
STATEMENT OF PROCEEDINGS

SAN DIEGO COUNTY SANITATION DISTRICTS

REGULAR MEETING

WEDNESDAY, JANUARY 10, 2007, 9:00 AM

Board of Supervisors North Chamber

1600 Pacific Highway, Room 310, San Diego, California

Meeting was called to order at 9:00 a.m.

PRESENT:  Directors Ron Roberts, Chairman; Greg Cox, Vice-Chairman; Dianne Jacob, 

Pam Slater-Price; Bill Horn; also Thomas J. Pastuszka, Clerk.

Approval of Statement of Proceedings/Minutes for the meeting of December 13, 2006 

ACTION:

ON MOTION of Director Jacob, seconded by Director Cox, the Directors of the San Diego County Sanitation Districts approved the Statement of Proceedings/Minutes for the meeting of 
December 13, 2006, on Consent.

AYES:  Cox, Jacob Slater-Price; Roberts; Horn
Public Communication:  [No Speakers]

Sanitation Districts Agenda Items


	1.
	LAKESIDE SANITATION DISTRICT

ESTABLISH APPROPRIATIONS FOR CONSTRUCTION OF LOS COCHES SEWER IMPROVEMENTS NEAR PANORAMA MOBILE HOME PARK (DISTRICT: 2)

(4 VOTES)



	2.
	SPRING VALLEY SANITATION DISTRICT

COUNTY OF SAN DIEGO TRACT NO. 5230-1: APPROVAL OF AMENDMENT TO JOINT AGREEMENT TO IMPROVE SUBDIVISION INCLUDING SUBSTITUTION OF PARTIES FOR PUBLIC AND PRIVATE IMPROVEMENTS LOCATED IN VALLE DE ORO COMMUNITY PLAN AREA (DISTRICT: 2)

(RELATES TO BOARD OF SUPERVISORS AGENDA NO. 10)



	SAN1.
	SUBJECT:
	LAKESIDE SANITATION DISTRICT

ESTABLISH APPROPRIATIONS FOR CONSTRUCTION OF LOS COCHES SEWER IMPROVEMENTS NEAR PANORAMA MOBILE HOME PARK (DISTRICT: 2)

	
	OVERVIEW:

	
	The Los Coches Creek Sewer was constructed in 1966 to transport sewage through Lakeside and downstream into the Lakeside Sewer Interceptor. The Department of Public Works has completed plans to replace sewer pipe that is deteriorating and undersized between Manholes 1 and 7 (Thomas Guide page 1232, E-6) north of Business Route 8.  

On September 21, 2005 (SAN 1), the Board authorized $1,000,000 for advertisement and award of a construction project to replace sewer pipeline for the Los Coches Creek Sewer.  Construction bids were opened on May 18, 2006.  TC Construction, Inc. was the only bidder on the project.  Their bid of $1,824,226 was over twice the amount of the engineer’s estimate 
($906,000) and exceeded the $1,000,000 authorized for construction by the Board of Supervisors.  The project bid was determined not to be competitive and was subsequently rejected on June 16, 2006.   

Based on discussions with the rejected bidder and other contractors that reviewed the plans but did not bid on the project, staff conducted additional soil investigations at the project site and revised the design plans and specifications to minimize project uncertainties and improve construction site access for contractors.  This will provide prospective bidders with better project information that should result in receiving more competitive bids. Staff has now revised the engineer’s estimate, increasing it to $1,650,000. The revision reflects site access difficulties, a larger extent of adverse soil excavation conditions than originally anticipated, and increased construction/materials unit costs.  

To provide adequate funds for construction and contingency this is a request to establish additional appropriations of $850,000 based on available funds in the Lakeside Sanitation District.  If approved, the project will be re-advertised by the Department of Purchasing and Contracting, and subsequently awarded to the lowest responsible bidder.  Construction of the Los Coches Creek Sewer Improvement project is anticipated to begin in May 2007 and be completed by October 2007. Because it is in a creek bed, this schedule avoids the rainy season to minimize creek dewatering needs and project delays due to rain events.

	
	FISCAL IMPACT:

	
	Funding in the amount of $1,000,000 was approved in Fiscal Year 2005-06.  This request establishes appropriations in the amount of $850,000 based on fund balance available in the Lakeside Sanitation District.  If approved, this request will result in $1,850,000 current year cost, no annual cost, and will require no additional staff years.  There will be no fiscal impact to the County General Fund.

	
	RECOMMENDATION:

	
	CHIEF ADMINISTRATIVE OFFICER
1. Find that the Mitigated Negative Declaration (MND) on file in the Department of Public Works for the Los Coches Creek Sewer Replacement Project was adopted in compliance with the California Environmental Quality Act (CEQA) and State and County Guidelines, that the Board has reviewed and considered the information contained therein prior to approving the project, that the MND reflects the independent judgment and analysis of the Board; and,

Find that there are no changes in the project or circumstances under which it is undertaken involving significant new environmental impacts not considered in the previously adopted MND, or a substantial increase in the severity of previously identified significant effects, and that no new information of substantial importance has become available since said MND was prepared.

2. Establish appropriations of $850,000 in the Lakeside Sanitation District for the Los Coches Creek Sewer Improvements near Panorama Mobile Home Park based on fund balance available.  (4 VOTES)

	
	ACTION:

	
	ON MOTION of Director Jacob, seconded by Director Cox, the Directors of the San Diego County Sanitation Districts took action as recommended, on Consent.
AYES:  Cox, Jacob, Slater-Price, Roberts, Horn

	
	

	

	SAN2.
	SUBJECT:
	SPRING VALLEY SANITATION DISTRICT

COUNTY OF SAN DIEGO TRACT NO. 5230-1: APPROVAL OF AMENDMENT TO JOINT AGREEMENT TO IMPROVE SUBDIVISION INCLUDING SUBSTITUTION OF PARTIES FOR PUBLIC AND PRIVATE IMPROVEMENTS LOCATED IN VALLE DE ORO COMMUNITY PLAN AREA (DISTRICT: 2)

	
	OVERVIEW:

	
	This project is a subdivision consisting of 9fillin "" \d "" single-family residential lots, 1 private street lot, and a total of 2.99 acres. It is located in the Valley De Oro Community, at the east end Hollyhock Road fillin "" \d ""(Thomas Guide, Page fillin "" \d ""1271, B-4).
This project is being brought before the Board for approval of Amendment to Joint Agreement to Improve Major Subdivision County of San Diego Tract No. 5320-1 (Substitution of Parties) for public and privatefillin "" \d "" improvements.

	
	FISCAL IMPACT:

	
	N/A

	
	RECOMMENDATION:

	
	CHIEF ADMINISTRATIVE OFFICER

Acting as Board of Directors of the Spring Valley Sanitation District:

Approve and authorize Clerk of the Board to execute Amendment to Joint Agreement to Improve Subdivision, (Including substitution of Parties)   (Attachment B).

(Relates to Board of Supervisors Agenda No. 10)

	
	ACTION:

	
	ON MOTION of Director Jacob, seconded by Director Cox, the Directors of the San Diego County Sanitation Districts took action as recommended, on Consent.
AYES:  Cox, Jacob, Slater-Price, Roberts, Horn


There being no further business, the Board adjourned at 9:02 a.m. 

THOMAS J. PASTUSZKA

Clerk of the Board of Directors

of Sanitation Districts

Notes By: Francia

NOTE: This Statement of Proceedings sets forth all actions taken by the County of San Diego Board Directors of Sanitation Districts on the matters stated, but not necessarily the chronological sequence in which the matters were taken up.

1/10/07







4

