## Noise Comments
PROJECT NAME: |  |  | JVR Energy Park | Project Number(s): | PDS2018-GPA-18-00
Specialist Name: |  |  | Souphalak Sakdarak | Project Manager Name: | Nicholas Koutoufidis
PDS (Planning & Development Services) Planning and CEQA Comments
Item | No. | Subject Area | Issue, Revision or Information Required | Issue Resolution Summary (Include Conditions) | Date Identified | Date Resolved
1- | 1 | Noise | Staff has reviewed the Acoustical Site Assessment for GPA-18-010, prepared by Dudek, dated May 2019 and submitted to the County on May 2019. Staff have the following comments: Staff has reviewed the Acoustical Site Assessment for PDS2018-MUP-8-002. Additional comments are provided directly on the report dated Dec. 2019. | General note. | 2019-06-07 | N/A
1- | 2 | Noise | In the Executive Summary page, first paragraph, remove the parenthesis and "Proposed Project". | It doesn’t change the content of the report | 2019-06-07 | 2020-01-17
1- | 3 | Noise | In the Executive Summary, adding the "expected" seems to indicate that the project may also be expected to not operated continuously. Please remove. |  | 2019-06-07 | 2020-01-17
1- | 4 | Noise | In the Executive Summary, please add a brief summary of why the acoustical assessment for the SDGE "Kettle One" was also analyzed in the report. | Information removed. The switchyard is one of the components of the project | 2019-06-07 | 2020-01-17
1- | 5 | Noise | In the Executive Summary, 3rd paragraph, remove "aka". | Information removed. | 2019-06-07 | 2020-01-17
|  | Noise | In the Executive Summary, 3rd paragraph, please explain "California", is that a name of the development? Typo? | Removed | 2019-06-07 | 2020-01-17
1- | 6 | Noise | Page 1, Project Description, add "within the County of San Diego's jusrisdiction" after "private land". | Added | 2019-06-07 | 2020-01-17
1- | 7 | Noise | Page 2, revise the second sentence to make it clearer. Maybe reword to say, "“The noise measurements were conducted near Noise Sensitive Land Use locations for 10 minutes at each area as depicted in Sites ST1 through ST6 as shown on Figure 4.” |  | 2019-06-07 | 2020-01-17
1- | 8 | Noise | Figure 4, what's the difference between the Sensitive Receptors B1 through B3 and R1 through R6? Does that represent Biological and Residential? Please clarify on the Figure, unless the allowable noise limits (decibels) are the same. If this measurement are discussed later in the report, still provide a brief explanation and maybe indicate further details are outlined in later sections? | See additional comments Directly on the Noise Report dated Dec. 2019 | 2019-06-07 | 2020-01-17
1- | 9 | Noise | Page 2 through 3, move the results from the measurements to the the Measuring Methodology section. The results of the measurements should be discussed after introducing the method used. | Revised | 2019-06-07 | 2020-01-17
1- | 10 | Noise | Page 3, after the second sentence, add a sentence that indicates, “The sound level measurement were measured with a sound level meter using the A-weighted and “slow” response. This is pursuant to the Noise Ordinance, Section 36.403. | Added | 2019-06-07 | 2020-01-17
1- | 11 | Noise | Page 23, Section 3.2.4. Please add a description of what is included in the equipment noise. Is it noise from the mechanical unit? Please add a sentence to introduce the equipment analyzed in the beginning of this paragraph. | Added | 2019-06-07 | 2020-01-17
1- | 12 | Noise | Page 25, first paragraph, the +3 dB for ambient noise only applies if the existing ambient noise levels already exceeds the Noise Ordinance levels, Table 36.404. Please specify that information or remove since it appears to not apply in this situation, taken the measured ambient noise is below the allowable 45 dBA. | Sentence revised | 2019-06-07 | 2020-01-17
1- | 13 | Noise | Page 17, under “Off-Site Direct and Cumulative Noise Impacts” section stated it is anticipated that up to 500 construction workers per day. However, page 26 mentioned about 200 workers. Please clarify. | Information on trips clarified. Additional comments added directly on Noise report dated Dec. 2019 | 2019-06-07 | 2020-01-17
1- | 14 | Noise | Page 17, last paragraph, does this analysis apply only to the temporary construction noise? Or does it apply to vehicles for the project operation as well? Please also provide an analysis of the noise impacts this project would have from its operational ADT. For example, as a daily operation for this project, how many ADT will it generate? Is it only for I-8 or will any other roadways be impacted? Will the project implementation result in the exposure of any off-site , existing or reasonably foreseeable future NLSU to exterior or interior noise in excess of any of the following: 1) exterior locations of 60 dB (CNEL)2 or an increase of 10 dB (CNEL) over pre-existing noise? | paragraph added to explain about traffic generated for the operation | 2019-06-07 | 2020-01-17
1- | 15 | Noise | Page 27, "Proposed Project" section. add the allowable hours of operation pursuant N.O Section 36.408. | Revised | 2019-06-07 | 2020-01-17
1- | 16 | Noise | The infroduction mentioned that the "Kettle One" switchyard, is this the same switchyard that is proposed for this project? Or is the report looking at this for refence to the noise levels. Did not see the analysis in the report besides the introduction. |  | 2019-06-07 | 2020-01-17

## Submittal Requirements
SUBMITTAL REQUIREMENTS FOR SCOPING/ITERATION LETTER
Date Requested | Name of Study | Number of Copies Required
| Revised Noise Report | Planner (1); Specialist Name (1)

## Specialist tracking
| Scoping | First Iteration | Second Iteration | Third Iteration | Fourth Iteration | Fifth Iteration
Date Submitted:
Date of Study:
Name of Specialist Reviewing:
Date of Site Visit (if applicable)
Enter balance of PDS account (check KIVA financial resp. screen): If funds are not adequate to complete your review, stop review and email project manager asking how to proceed
MOU Required and Submitted? (Yes, No, or N/A) (required if project scoped on or after July 1, 2006)
Consultant on applicable list? enter "yes", "no" or "N/A"
Does study comply with applicable Guideline for Determining Significance and Report Format and Content Requirement? (Yes, No, or N/A) Required if project was scoped after approval of the relevant Guideline
Make KIVA entry made in the "comment" field. Enter either "Incomplete","Accepted" or "Accepted with Minor Revisions"
If study accepted, have you completed Initial Study Responses and provided Project Manager with Conditions and/or Mitigation Measures? w
Completed Consultant Evaluation Form and emailed to Don Kraft? Always fill out form if Guidelines not followed, for notable poor performance, and when review is accepted.