## Landscape Comments
PROJECT NAME: |  |  |  | Project Number(s):
Specialist Name: |  |  |  | Project Manager Name:
Item | No. | Subject Area | Issue, Revision or Information Required | Issue Resolution Summary (Include Conditions) | Date Identified | Date Resolved
PDS (Planning & Development Services) Planning and CEQA Comments
| 1 | Landscape
| 2 | Landscape
| 3 | Landscape
| 4 | Landscape
| 5 | Landscape
| 6 | Landscape
| 7 | Landscape
| 8 | Landscape
| 9 | Landscape
| 10 | Landscape
| 11 | Landscape
| 12 | Landscape
| 13 | Landscape
| 14 | Landscape
| 15 | Landscape
Note on E5: When the project is resubmitted, indicate in this column whether the comment was addressed adequately or not. If the comment was not addressed, describe what additional information is needed.

## Landscape Comments -xxx
PROJECT NAME: JVR Energy Park |  |  |  | Project Number(s): PDS2018-REZ-18-007
Specialist Name: David Kahler |  |  |  | Project Manager Name: Bronywn Brown
Item | No. | Subject Area | Issue, Revision or Information Required | Issue Resolution Summary (Include Conditions) | Date Identified | Date Resolved
Planning & Development Services (PDS) Planning and CEQA Comments
| 1 | Landscape | Additional screening of the perimeter fencing shall be provided for all areas visible from Interstate 8 and Carrizo Gorge Road along the northern portion of the proposed facility. |  | 2018-11-21
| 2 | Landscape | Additional screening of the perimeter fencing shall be provided along the western edge of the area adjacent to Seely Ave. and continue along the notheastern edge to establish screening from views of adjacent property owners within the central portion of the proposed facility. |  | 2018-11-21
| 3 | Landscape | Screening of the perimeter fence, as seen from Old Highway 80 and Carrizo Gorge Rd. along the eastern edge of the central portion of the proposed facility shall also be provided. |  | 2018-11-21
| 4 | Landscape | Continue permiter fence screening south, to a point that surrounding property owners will not be impacted visually, along the western edge of the southern portion of the proposed facility. |  | 2018-11-21
| 5 | Landscape | Coordinate with the project biolgist and label the adjacent habitat types aroud the permiter of the site and place a note that states all planting required for screening adjacent to these areas will be established with vegetation typical of that particular habitat. |  | 2018-11-21
| 6 | Landscape | Provide a note that states all required screening of the site will extend until such time as area topography or distance from viewpoints can be determined not to be a significant visual impact. |  | 2018-11-21
| 7 | Landscape | Show screening of the perimeter fencing for both the proposed SDG&E Switchyard and the Substation facility. |  | 2018-11-21
| 8 | Landscape | Provide notes that clarify what sections of the Jacumba Community Service District Guidelines are being addressed and how the proposed landscape layout will satisfy these requirements. |  | 2018-11-21
| 9 | Landscape | Clarify the source of water for all area landscape irrigation. Note 3 on the title sheet to the conceptual landscape plans states that irrigation will be connected to a domestic water meter and Sheet 104 of the Major Use Permit plot plan shows two existing wells labeled to be used for area irrigation. Please make necessary revisions. |  | 2018-11-21
| 10 | Landscape | Provide an approximation of all area landscape irrigation demands during the plant establishment period (see definition within the Water Conservation in Landscaping Ordinance) and on a yearly basis thereafter using the Estimated Total Water Use formula within the Ordinance. Include the use of irrigation for erosion control planting associated with the projects grading plan. This information shall be provided as part of the Conceptual Landscape Plan and also provided for use in estimating the overall demand for water usage for the proposed project in other documention required by the County. Provide values for both temporary and permanent irrigation uses. |  | 2018-11-21
| 11 | Landscape | Provide a note that states all disturbed areas associated with construction of the site will be re-planted/re-seeded with vegetation typical to the particular habitat type where the disturbances occur. This includes all temporary and permanent impacts to the site and surrounding areas. Note how temporary or permanent irrigation will be provided to establish vegetation. |  | 2018-11-21
| 12 | Landscape | Coordinate with the project biologist and show the locations of all Environmentally Sensitive Areas. |  | 2018-11-21
| 13 | Landscape | Verify that the images shown on the plant cross sections are true representations of nursery standard container sizes based on species proposed at time of planting, and during the life span towards maturity. Some images of the graphics shown apprear to be too large for the scale of the drawings. Please review and ensure the graphics shown and the sizes are typical of the species proposed in these areas. Consider labeling height and width of species on cross sections to better define scale. |  | 2018-11-02
| 14 | Landscape | Clarify if area boulders exposed during grading activities will be utilized within the area landscaping. Show locations within buffer landscaped areas. |  | 2018-11-02
| 15 | Landscape | Clarify if native soils will be salvaged and stockpiled for use in future establishment of native vegetation in areas appropriate for their re-use. |  | 2018-11-21
| 16 | Landscape | Provide a list of all proposed seed mixes to be used in areas adjacent to native habitat types. |  | 2018-11-21
| 17 | Landscape | Coordinate with Note 5 on Sheet 400 and provide a separate sheet within the Conceptual Landscape Plan that identifies the species, location, and size of all existing trees to remain, and those to be removed. Identify the location and species of all masses of existing shrubs to remain, and those to be removed. Provide notes about how existing vegetation to remain will be protected during construction of the site and what replacement measures are proposed for those specimens that are damaged during construction. |  | 2018-11-21
Note on E5: When the project is resubmitted, indicate in this column whether the comment was addressed adequately or not. If the comment was not addressed, describe what additional information is needed.
Note on D7: Insert Community name or delete if not applicable.
Note on D9: Insert specific sheet

## Sample Comments
Choose applicable sample comment language for insertion into your project specific comments. The following is boilerplate language for convenient cut and pasting into the actual comments sheet.
Topic | Sample Comment Language
Landscape | Note - Requirements for landscaping are based on the County of San Diego’s Landscape Water Conservation Design Manual, the County of San Diego Off-Street Parking Design Manual, and the _____ Design Review Board Guidelines.
Landscape | Per the Off Street Parking Design Manual, ________
Landscape | Per the__________Design Guidelines for Commercial Development,
Landscape | Provide a note on the landscape plans, (sheet ____ ) that states how _____
Landscape | Provide a note on the landscape plans (sheet ____ ) that indicates who will be responsible for on-going maintenance of the landscaping, including the public right-of-way.
Landscape
Landscape
Landscape
Landscape
Landscape
Landscape
Landscape
Landscape
Landscape
Note on B5: Insert Community name or delete if not applicable.
Note on B6: Insert specific sheet
Note on B7: Insert specific sheet #

## Specialist checklist
| First Iteration | Second Iteration | Third Iteration | Fourth Iteration | Fifth Iteration
Date Submitted:
Date of Study:
Name of Specialist Reviewing:
Enter balance of DPLU account (check KIVA financial resp. screen): If funds are not adequate to complete your review, stop review and email project manager asking how to proceed
MOU Required and Submitted? (Yes, No, or N/A) (required if project scoped on or after July 1, 2006)
Consultant on applicable list? enter "yes", "no" or "N/A"
Does study comply with applicable Guideline for Determining Significance and Report Format and Content Requirement? (Yes, No, or N/A) Required if project was scoped after approval of the relevant Guideline
Make KIVA entry made in the "comment" field. Enter either "Incomplete","Accepted" or "Accepted with Minor Revisions"
If study accepted, have you completed Initial Study Responses and provided Project Manager with Conditions and/or Mitigation Measures? w
Completed Consultant Evaluation Form and emailed to Don Kraft? Always fill out form if Guidelines not followed, for notable poor performance, and when review is accepted.