## Lessons Learned
Lesson Learned Topic 1 | Lesson Learned Topic 2 | Submitted By | Category | Description | SWOT Analysis | Action | Recommendation
Legislation | NA | David Bame | Doctrine | Changes to IRC's governing laws could improve effectiveness & efficiency. 9 votes could be required only for mapping and other major decisions, with 8 required for more process issues like hiring and contract approval. Delays in census data do not change the need for sufficient time for public input and IRC reaction during the mapping period. | Opportunity | Modify | -Apply 9-vote requirement only to mapping/major decisions, & 8 votes on admin/hiring decisions -keep periods b/w receipt of SWDB data & final map approval, & b/w IRC’s first map and final map, regardless of census delays -consider 7-work day period b/w release and approval of final map, for ROV and other requests for technical changes
Legislation | NA | Amy Caterina | Finance | Commissioners were not compensated for their time. | Weakness | Modify | This situation is codified in the law, but many commissioners put in excessive time and should be compensated, similar to State CRC, although maybe not at the same level. A transition team could reach out to the legislators and ask to have this considered for all Independent Redistricting Commissions.
Legislation | Commissioner Selection | Inman | Organization | While delays in Census data release caused all kinds of problems, there was one benefit. Our commission gained additional time to plan and prepare. Without that additional time we would not have succeeded. Basically we ended up starting in Dec and finishing a year later. | Opportunity | Modify | Start commission in August to give them 12 months.
Legislation | Commissioner Selection | Rosette Garcia | Policy | The 2020 IRC was not fully seated until December 2020, and, in "normal" circumstances (no COVID-19 disruption and no Census delays), would have been required to ramp up all activities (training, governance rules, procurement of contractors, outreach, timeline planning, etc.), receive data by Apr 1 and complete mapping by Aug. 15. | Weakness | Modify | Recommend seating full IRC earlier--by Sept 1. It is optimistic (unrealistic) to expect 14 strangers, likely with no redistricting or public commission experience, to learn/do what is needed in 4 months (Jan-Apr) before starting complex task of drawing new maps. 2020 IRC had from Jan-Sept before mapping; 2030 should get similar time.
Legislation | NA | Sonia Diaz | Policy | Lack of political will to modify redistricting deadline to January 15th to allow for more public comment. | Opportunity | Modify | Review the statute that creates San Diego IRC and introduce legislation that would allow for the flexibility of any dates to be modified in the event of process delays.
Commissioner Selection | NA | Sonia Diaz | Doctrine | Commissioner recruitment not as diverse as it could be. | Weakness | Modify | Start recruitment early – at least one year before the next redistricting cycle (2029) - an aggressive community outreach to recruit diverse body of applicants utilizing a variety of methods via television/radio PSA, e-list servs, print and digital ads on social media. Publicize at existing community venues/groups: o CBOs and volunteers already engaged in Census outreach o Community Planning Groups o Town Council Meetings o PTA meetings o Places of worship o Recreation centers and libraries Civic engagement clubs at community colleges and universities
Commissioner Selection | NA | Sonia Diaz | Doctrine | Timeline for commissioner application submission and review | Strength | Modify | The deadline for applications should be moved to spring (March/April) with an application review period moved up at least one to two months earlier. This would have the final 60 applicants that move onto the lottery stage happen in June so that the supervisorial meeting to select the first 8 can occur in August with the first IRC meeting to happen in September/October instead of November.
Commissioner Selection | Other | Rosette Garcia | Facilities | Laptops, headphones, etc. | Weakness | Modify | County staff should prepare in advance so that all equipment is procured and ready to distribute from the day that commissioners are selected, including clear process for how materials will be delivered.
Commissioner Selection | NA | Arv Larson | Leadership | Even though we were a small group working to a common purpose, there was relatively little opportunity to get to know and socially interact with fellow Commissioners. Most interactions and opportunities to better understand our peers on the IRC were limited. Initial and ongoing social gatherings enable people to build rapport and mutual understanding. Such gatherings facilitate communications and team building. The IRC chairman seemed to recognize the need for such social interaction but did not attempt actionable follow-up at any point. Small groups of Commissioners did exchange occasional non-IRC business pleasantries over random snacks or session breaks, but one had to make a real effort to informally get to know one's peers and understand where they were coming from in their meeting dialog. There was not an initial "get-to-know-you" event nor a close out celebratory gathering to congratulate ourselves on completing our efforts. | Weakness | Modify | Appoint an ad hoc committee to schedule and organize a series of non-business gatherings such as a potluck lunch or dinner in public or private spaces. All IRC and staff would be invited but with no pressure to attend. Also schedule occasional all-IRC "Happy Hour-type" social gatherings somewhere with free parking. All participants in these activities would understand to be careful to avoid any Brown Act violations.
Commissioner Selection | NA | Amy Caterina | Material | Computers were provided to commissioners. | Opportunity | Modify | computers were managed through an external provider. Commissioners were not set up under the County IT program (for external computer use and support) and as a result Commissioners faced work interruptions, delays and other inconveniences. The new IRC computers should be set up with the same parameters as county employees.
Commissioner Selection | NA | Ponds | Material | IT equipment. The late delivery of IT resources distracted from the IRDC process. | Weakness | Modify | Identify and deliver IT resources to Commissioners during the initial stage of the redistricting process.
Commissioner Selection | NA | David Bame | Material | IT support for Commissioners, including use of tablets & cell phones as well as software, could be more targeted and scheduled. Such challenges as forced software updates and lack of access on mobile devices can inhibit IRC work at particularly important moments. | Opportunity | Modify | IRC staff should work earlier (e.g. by the 3rd full IRC meeting) and more often with IT staff on IRC-approved IT tasks, including access to mobile devices; "fenced-off" periods, especially during mapping, with software updates to occur before or after such periods; and a clear retention policy for IRC emails and documents.
Commissioner Selection | NA | Amy Caterina | Organization | The IRC was fortunate to include among its commissioners, a demographer, legal experts, communications experts, procurement expert, financial and business experts, engineers and community advocates. | Strength | Modify | The new IRC should be composed of a similar group of commissioners as much as possible. Aggressive advance promotion of the new IRC in each of the five districts will help insure that there is a great base of candidates from all five districts from which to choose. The transition team could facilitate.
Commissioner Selection | NA | Sonia Diaz | Organization | 14-members that are citizen volunteers | Strength | Modify | To increase the pool of diverse applicants that may have financial barriers to participating (mostly younger adults with families, college students, non-retired adults), I would suggest offering a symbolic stipend (flat per diem rate) for each meeting attended.
Commissioner Selection | NA | David Bame | Personnel | The IRC selection process of 60 finalists, 8 commissioners selected by lottery, and 6 selected by the 8 initial commissioners seemed to insulate against real or perceived political interference. There was no need for retired judges or other actors to be involved in a process that could have put IRC independence at greater risk. | Strength | Continue | The IRC selection process should remain the same, perhaps with additional energy spent on encouraging applications from hard-to-reach County residents.
Commissioner Selection | NA | David Bame | Personnel | The County should consider ways to encourage a greater pool of applicants from all parts of the County, including possible financial or other incentives & compensation to Commissioners appropriate for a decennial commission. The County also should consider accepting IRC interns from hard-to-reach communities, universities, and civic groups. | Opportunity | Modify | County staff could work with previous IRC commissioners & civic leaders to expand the pool of applicants & build an effective intern program.
Commissioner Selection | Training | David Bame | Training and Education | Exchanges with other current redistricting commissions and with past commissioners could provide useful insights and foster out-of-the-box thinking. | Opportunity | Modify | The full IRC may want to consider hosting a social event or video conference with former redistricting Commissioners. The IRC may also want to consider joint training opportunities as a means to establish contact and exchange ideas with other local and regional commissions.
Budget | NA | Amy Caterina | Finance | Commissioners monitored the financial status of the IRC. Staff provide budget updates and monthly financial reports to the IRC. An Ad Hoc Committee was formed to analyze the financial status and create a budget. | Opportunity | Modify | The IRC should receive the final financial update from staff with detailed expenses (including the final County outlay for staff and various resources (total staff salaries, any DPC , County Counsel and County Communications expenses incurred). The IRC needs to know the total amount expended. The new IRC should decide who manages finances.
Budget | NA | Arv Larson | Finance | The initial IRC budget and financial staff were provided to the IRC by the COSD. As it turned out, the initial budget was not adequate to meet the performance needs of the IRC. All financial oversight was first developed by the COSD-assigned staff with after-the-fact reports provided to the IRC. The initial cost estimates for general and special counsel and service contractors were low, were subsequently modified by an IRC ad hoc committee, and required additional funding from the BOS. There was no independent "Treasurer" function reporting only to the IRC. | Weakness | Modify | Appoint an IRC Commissioner to serve as Treasurer and establish a regular Budget committee for oversight of all IRC financial activities. Establish a working budget early on, revise as necessary as anticipated costs become clearer, and obtain additional funding resources from the BOS early in the redistricting cycle. Provide bi-monthly budget reports to the IRC.
Budget | NA | Commissioner Brown | Finance | Money side of the map drawing process. | Strength | Continue | 1. Get budget upfront for the commission from the County. 2. Have County staff prepare and present the monthly budget at the last commission meeting of each month. 3. Gives Commission a guideline for expected upcoming Request for Proposal expenses and miscellaneous expenses.
Budget | NA | Ponds | Finance | Fiscal Oversight. The IRDC encountered financial management and budget (FMB) planning and implementation challenges, including but not limited to a lack of involvement in 1) developing the FMB process, 2) creating audit and oversight policies and protocols, and 3) determining the utility of discretion funding to support low-cost/hi-yield expenses. | Threat | Modify | Revise FMB policy, protocols and processes to include Commissioners in the initial stages of design, development and execution, including a discretionary fund line item to allow Commissioners the flexibility and agility to respond to short notice and unforeseen requirements.
Budget | Personnel - Consultants - General | Rosette Garcia | Finance | Budget | Opportunity | Modify | Recommend 2030 IRC consider using County staff for outreach/communications as they have considerable existing resources/staff that would likely result in more efficient/effective/fiscally prudent processes and deliverables, AND make available more funding for demographer consultant, a high priority for resource allocation.
Budget | NA | Sonia Diaz | Finance | Budget process needs to be developed and managed solely by the IRC not county staff and needs further refinement | Weakness | Modify | See comment above about establishing Budget Subcommittee
Budget | NA | David Bame | Finance | The regular monthly budget updates provided a useful method to review IRC budget activities & ensure compliance with good governance practices. An even earlier focus on the budget would make the process even more effective & transparent. A Budget Ad Hoc Committee could help, & a Legal Budget AHC may be useful for those more complex matters. | Strength | Modify | The IRC, perhaps working from a Budget AHC, should approve a sufficiently detailed budget in its first month of work. A Legal Budget AHC should also be considered. The IRC also should plan early for any possible supplemental request, to ensure such a request is made only once to address all budget requirements.
Budget | NA | Rosette Garcia | Policy | No clear policy exists for handling potential or proposed budget amendments, contract amendments or reallocation of funds. In other words, is review and approval of such changes required, particularly when no new funds are necessary (changes maintain existing bottom line), and, if so, by whom? | Opportunity | Modify | Develop a clear policy for handling budget and contract amendments, even if such changes can be paid for with existing funds. Clarify whether approval is required in advance of changes and if so by whom and using what process-- chair/officers, staff (executive lead), or designated comm'r or committee.
Budget | NA | Rosette Garcia | Training and Education | Budget setting | Opportunity | Modify | Assign comm'rs with expertise or interest to Budget & Finance Comm or Working Group to begin working with staff to develop a budget for approval by full IRC.
Bylaws | Training | David Bame | Doctrine | Given that Commissioners are chosen in part to reflect the political diversity of the County, including through their own respective political party membership, early discussion and agreement to clarify allowed political activity and participation is important to public trust in the IRC. | Threat | Modify | Further refine, through IRC discussion and vote, agreed guidelines and limits in Elections Code and IRC Bylaws on Commissioner participation in political party meetings & events, disclosure of contacts with political actors (including those outside formal parties), and other such political activity.
Bylaws | Leadership | Sonia Diaz | Leadership | Executive officers need clearly defined roles and responsibilities; maintain nonpartisanship. | Weakness | Modify | Update the Bylaws to provide clearly defined and specific responsibilities for all Executive Officer positions and require that there be partisan balance (e.g., two Co-Chairs representing each party). The ideal structure would be the following: Two Co-Chairs, Secretary, Parliamentarian, and a Treasurer. Ideally, each of the five officers elected represent a different supervisorial district. The Co-Chairs will share the responsibility of conducting meetings, developing the meeting agenda, inviting guest speakers where appropriate, and ensuring that deliberations from both the general public and Commissioners go as smoothly as possible during meetings. The Secretary would work with County Staff (Clerk of the Board of Supervisors) to ensure that the meeting minutes are accurate, will assist Chairs with the creation of the agenda, assist in community outreach for special projects (e.g., education tours, design of external-facing flyers of the Commission, proposal of new meeting venues, etc.). The Parliamentarian must be present at all meetings and will advise on parliamentary procedure, in consultation with General Counsel, and recommends amendments and updates to the Bylaws to the Commission. The main role of the Parliamentarian is to support the Co-Chairs during each meeting to ensure smooth flow of meetings (a lot of this work is already done by the Clerk but will support this role, especially managing public testimony as the meetings are heavily attended toward the end). The Treasurer chairs the Budget Subcommittee and is the Commission liaison for all budgetary matters before the Commission; this includes submitting formal requests (with Commission approval) to the Board of Supervisors. After the monthly budget report is approved by the Budget Subcommittee, the Treasurer reads and presents the report during the regular Commission meetings.
Bylaws | NA | Commissioner Brown | Policy | Commission Bylaws. | Strength | Continue | Review Bylaws as soon commission is sworn in and update as needed.
Leadership | NA | Amy Caterina | Leadership | The IRC had three officers and two single points of contact. These individuals were kept extremely busy managing their various responsibilities. | Opportunity | Continue | The structure is reasonably sound, but expanding the executive team could be advantageous. A rotating chair could help reduce burnout and even out the workload over the redistricting period. Identifying an individual spokesperson would reduce the load on the Chair.
Leadership | Personnel - Consultants - General | Commissioner Brown | Leadership | One Chairperson with two Co Chairperson's. Ad hoc committees with Persons of Contact for large contracts; demographics, media and legal contractors. | Strength | Continue | Two Co Chairs help balance the workload of the Chairperson. Point of Contact with the large contractors helps keep the commission aware of progression and problems. Ad hoc committees eliminated the public notice constraints brought on by the Brown Act. Small committees with a specific purpose disbanded when the purpose was accomplished.
Leadership | Bylaws | Jack Russ | Leadership | Chairman/Vice Chair roles. | Opportunity | Modify | Possible rotate chairing meetings between the elected officers. Different modes of leadership could possible change the character of the conversation which was mostly many micro-monologues.
Leadership | NA | Kristina Kruglyak | Leadership | Chair | Strength | Continue | Maintain single Chair. This allows for continuity and uniformity.
Leadership | NA | Ponds | Leadership | Ad Hoc and Subcommittees: Proved instrumental in the success of the Independent Redistricting Process. However, Commissioners were volunteers, randomly selected based on preference and served simultaneously on several committees. This approach created excessive individual work loads and failed to leverage Commissioner's expertise and experience. | Weakness | Modify | Continue to utilize committees to support the IRDC process, ensuring that each and every Commissioner have an opportunity or are assigned to a committee based on expertise and experience.
Leadership | Bylaws | Ponds | Leadership | Chair and Co-Chairs. Utilizing the Chair and Co-Chair construct proved valuable to the redistricting process. However, both Chair and Co-Chairs were often overloaded in executing their demanding roles and responsibilities. | Opportunity | Modify | Maintain the Chair and Co-chair construct and establish a process to rotate Co-chairs into the Chair position to ensure workload balance and continuity.
Leadership | Bylaws | Rosette Garcia | Leadership | Bylaws allow for a chairperson and one or more vice chairs, and may rotate or serve simultaneously, but are elected only once after the full commission is seated. | Opportunity | Modify | I recommend rotating officers, allowing for more than one person to serve as chair, even allowing/planning for new officer elections throughout process to encourage parity of influence among 14 comm'rs. (would require bylaws amendment).
Leadership | Bylaws | Sonia Diaz | Leadership | Ad Hoc Committees did not adequately handle the magnitude of work before the IRC. | Weakness | Modify | Amend Bylaws to allow for, at a minimum, the creation of the following standing Committees: o Budget and Oversight – Chaired by the Treasurer of the IRC. Reviews all expenditures of the Commission and make recommendations for new expenditures; develop and approve a monthly expenditure report to the full Commission at regular meetings. Review and approve salaries for all contractors and subcontractors, contracts, and review of pro formas, and maintain a full public record of receipts for work rendered. o Community Outreach & Engagement – In collaboration with the Executive Director, develop a public outreach and engagement plan to be approved by the IRC. Provide ongoing support and direction to the Executive Director on venues for meetings Bylaws, and Community Outreach. Each of these meetings will require to adhere to the Brown Act and must post public agendas and hold their meetings in public.
Leadership | NA | David Bame | Leadership | The full IRC should carefully consider the benefits & costs of a permanent vs. rotating chair, including how many Commissioners participate in any rotation, & of how many vice-chairs to have. Questions of availability & continuity need answers in such discussions. More permanent duties may restrict leaders' taking positions in meetings. | Strength | Continue | The interim IRC should choose an interim chair & vice-chair to serve until at least the 3rd full IRC meeting, allowing Commissioners to consider best long-term options. Chairs & vice-chairs may need to spend up to 15 hours/week on IRC work. Officers should decide on how active they will participate in IRC discussions, and so inform the IRC.
Leadership | NA | David Bame | Leadership | Short-term leadership opportunities for all interested Commissioners helps build IRC shared ownership, participation, energy, and effectiveness. Officers and Commissioners alike can work to develop AHC & outreach opportunities, as well as suggestions that draw on Commissioners’ individual talents and experiences. | Opportunity | Modify | The IRC could develop a more specific, targeted plan for Commissioners to seek and fulfill leadership opportunities, especially in sharing ad hoc committee work, to foster more effective participation and contributions to the full IRC's work.
Leadership | Bylaws | Amy Caterina | Organization | The organizational structure of the IRC was established in the initial bylaws and was provided to the IRC. The bylaws were modified in early 2021 to reflect a Chair and two Co-Chairs. The Bylaws were then amended in the summer of 2021 to clearly define the roles and responsibilities of the commissioners as well as the officers. | Opportunity | Modify | Towards the end of the process, there was an uneven workload balance. The IRC should consider modifying the bylaws to establish a rotating Chair or Co-Chair scenario. The role of the Spokesperson should be more clearly defined and perhaps allocated to one individual as to reduce the workload of the Chair.
Leadership | NA | Rosette Garcia | Policy | Currently the Chair is the only spokesperson for the IRC and all requests for any public engagement much go through and be approved by the Chair. There was some discussion about delegating this duty to another commissioner or to a committee, but that never happened. | Weakness | Modify | Consider other options for how to handle interview requests, op-eds, other public engagement. On a 14-member commission, of 14 citizen volunteers, it is not necessary to funnel all of this activity through the one commissioner who already has numerous obligations. Comm'rs could apply for role; comm'rs could rotate in and out of role.
Training | Mapping Considerations | Commissioner Brown | Doctrine | Rules for the Commission to follow as it decides on it's final maps. | Opportunity | Continue | All voices are important. Commissioners should be representative of the entire county. Maps should be drawn without influence for political gain. The commission should follow the Voter's Rights Act, Bylaws, US and State Constitution requirements keeping in mind the Communities of Interest's requests to stay intact.
Training | Mapping Considerations | Rosette Garcia | Doctrine | The IRC was guided by its commitment to obtain as "broad and diverse participation" as possible. The IRC also took seriously its mandate to operate independently from the BOS. Equally important but less emphasized was commitment to be impartial and how/to what/if extent commissioners represent a district/COI/region etc. | Opportunity | Modify | Commissioners claim an ability to be impartial, a point that deserves equal emphasis and commitment, to avoid even the appearance of bias as well as commissioners acting as a member of, or an advocate for, a COI or other group. (This could also be a training item, to include pointing out that commissioners do not "represent" their district)
Training | Bylaws | David Bame | Doctrine | Commissioners were not sufficiently aware, from the beginning, that they were not chosen as representatives of their respective districts but rather for reflecting the County's political diversity. | Weakness | Modify | Perhaps amend bylaws to clarify clearly that commissioners do not represent their districts, but are instead expected to combine their knowledge of a given district with the knowledge of their colleagues.
Training | NA | K. Elliott | Material | The IRC received lots of material and information throughout the process that was relevant to discussion (e.g. population per city and per census designated place). This information was provided in static tables, materials, and in the web viewer. Throughout the meetings, IRC members seemed to have some difficultly locating materials on the webpage. | Opportunity | Modify | One recommendation is to have a separate "Materials" webpage to host all relevant materials all in one place for the IRC members to easily access. This could be linked to each agenda to remind IRC members and the public where to find these helpful materials.
Training | NA | Christian Grose | Organization | The Commission did a great job working to ask questions and providing feedback on the early RPV analyses. The Q&As were also illuminating. For the future, it may be helpful for the Commission to receive VRA/RPV training much earlier. The CA state commission did that. | Opportunity | Continue | For the future, it may be helpful for the Commission to receive VRA/RPV training much earlier. The CA state commission did that.
Training | Leadership | David Bame | Organization | Ad hoc committees are a useful tool to help the IRC make progress on key issues, preparing for a fully transparent and complete discussion and decision by the full IRC. AHC members helpfully avoided even the perception of exceeding their authority. | Strength | Continue | Continue to ensure the goals, authorities, and limitations of ad hoc committees are clearly understood by all Commissioners and the public, including through holistic summaries and updates of AHC work and through clearly defined tasks from the full IRC.
Training | NA | Amy Caterina | Training and Education | Training and education were provided to the IRC, however, much of the training was conducted during meetings, which while helpful and informative, was delayed and very time consuming and detracted the Commissioners from conducting the business of the IRC. The Ad Hoc Committee developed an excellent training platform. | Opportunity | Modify | Would recommend conducting training earlier in the process. Perhaps through the development on publicly available online learning tools or providing early structured access to the Training Continuum. The current IRC should endeavor to provide a package of information to the next IRC which provides structured learning tools.
Training | NA | Arv Larson | Training and Education | I came into the IRC thinking I really knew something about the many COSD districts (administrative, geographic, school, water, fire, etc.) and their demographics but quickly found out that I needed a much improved understanding of these various entities and interests to best process and utilize our COI and other public input. | Opportunity | Modify | Conduct several hourly information sessions providing an overview of the many existent County organizational and regional entities as well as COI and ethnic demographics, localities, and history. Such training could be given by SANDAG and COSD officials and relevant staff (e.g., the Registrar of Voters, SANDAG/County outreach staff) in addition to County-based educators and appropriate subject matter experts.
Training | NA | Commissioner Brown | Training and Education | 1. Get Commissioners trained as soon as possible. | Strength | Continue | Initial training should include Voter's Rights Act, Brown Act, Bylaws, 14th and 15th Amends to the US Constitution, racial polarity and prior files with notes and maps from the previous redistricting plan. Prior information should include all maps, contracts, agendas, meeting minutes, structure, timelines.
Training | NA | Inman | Training and Education | We never had a comprehensive explanation of all the different geographic areas, jurisdictions, and boundaries that are impacted by redistricting or the implications that result if those entities are split by supervisorial districts. It was only late in the process that we learned about county planning districts or fire districts. | Weakness | Modify | Put together a training program on various geographic entities in SD County and implications if they are split.
Training | NA | Jack Russ | Training and Education | Learn county geography/topology. | Opportunity | Modify | Briefing on fire districts and planning groups locations
Training | NA | K. Elliott | Training and Education | It would be helpful to train the communications and outreach consultant on using the mapping tool. The consultant could then demo the tool during outreach events and help promote best practices for drawing and submitting maps. | Opportunity | Continue | Train the communications and outreach consultant on using the mapping tool and build in public demo/training into the communications consultant scope.
Training | Mapping Considerations | K. Elliott | Training and Education | Include pros and cons of different styles of map submissions as part of the community outreach effort. For example, we received a few community of interest maps that had a population close to above the ideal district population. Smaller COI geographies are more helpful and much more likely to be preserved. | Opportunity | Continue | Include training, education, and materials to demonstrate pros and cons of different styles of map submissions to emphasize importance of small COI geographies.
Training | NA | Kristina Kruglyak | Training and Education | Board of Supervisors | Weakness | Modify | Have Commissioners attend or at least get detailed recaps of the Board of Supervisors meetings, especially early in the process. It will be useful for commissioners to have a deep understanding of the types of questions/issues that the Supervisors address so that the needs of each constituency can be better understood.
Training | NA | Ponds | Training and Education | Training and Education. The IRDC Training Plan proved instrumental in the Commission's ability to execute its roles and responsibility effectively and efficiently and should be reviewed for its adequacy to ensure it is properly designed, developed, implemented, and facilitated. | Strength | Continue | Review IRDC training and education plan framework and process to maximize its effectiveness and efficiency.
Training | NA | Ponds | Training and Education | Environmental and Economic Impact Studies (E/EIS). The Redistricting process did not include information derived from Environmental and Economic Impact Studies (E/EIS). | Weakness | Modify | Conduct and incorporate E/EIS into the redistricting training and education, and map drawing process.
Training | NA | Rosette Garcia | Training and Education | Missing training module(s) | Weakness | Modify | Add training module: primer on IRC, commissioner duties, activities, bylaws, possible committee memberships, and other general onboarding (email, contacts). Specific topics to include what comm'rs can do (outreach, e.g.). Important for all comm'rs be on an equal playing field re access to info, staff, and other comm'rs.
Training | NA | Rosette Garcia | Training and Education | Training module missing | Weakness | Modify | Add training module: Training on County jurisdictions and governance (various city and county comm planning groups, fire districts etc.) and a review of the county regions, populations, existing known COIs. This info is essential in mapping and has implications in line drawing decisions.
Training | Mapping Considerations | Rosette Garcia | Training and Education | Mapping training | Weakness | Modify | More mapping training and consider doing some of this training early, often (repeatedly) and in small working groups.
Training | NA | David Bame | Training and Education | Early commitment to and use of training resources, including but not limited to public advocacy groups, can foster effective discussion as well as increased knowledge among Commissioners. | Strength | Continue | The IRC could draw on the 2021 training continuum to guide updated training in light of new technological and legal developments, particularly with regard to mapping, communities of interest, and outreach. A more County-specific module on such features as unincorporated areas and hard-to-reach communities may be useful.
Personnel - Support Functions | NA | Amy Caterina | Doctrine | A County employee was assigned as Executive Lead to the IRC and county based staffing were provided to the IRC. The Executive Lead as instrumental in the success of the IRC and the staff were responsive and professional. | Strength | Modify | The IRC should decide the organizational structure in respect to its doctrine and choose the structure that is most appropriate. An executive external to the county system might be beneficial as a spokesperson and overall outreach coordinator.
Personnel - Support Functions | Personnel - Consultants - Legal | Arv Larson | Organization | The Executive Director, support staff and outside general counsel were assigned to the IRC by the COSD. The IRC did not participate in this assignment. Selection and control of these resources, reporting responsibilities, and their independence from COSD leadership became an issue. It was never clear who was ultimately in charge or if there was undue control of IRC activities by COSD interests serving to diminish IRC decision independence. | Weakness | Modify | Following the independent selection of IRC membership, the IRC should solicit and hire an Executive Director, support staff, and outside general counsel. The COSD BOS should fund this effort but otherwise be uninvolved with IRC organizational and operational activities.
Personnel - Support Functions | NA | Amy Caterina | Personnel | This comment is related to the previous doctrine discussion. One of the early initial decisions was to have County staff provide support for the IRC. The staff provided was professional and thorough and was a significant asset to the IRC and the successful outcome of our process. | Opportunity | Modify | The IRC should choose the doctrines that define its operating structure and decision making paradigm. The new IRC should make the decision about staffing and personnel. A transition team should conduct analysis and provide options and recommendations to the new incoming IRC. The County should provide interim staff until a decision is made.
Personnel - Support Functions | Meetings - Planning | Commissioner Brown | Personnel | Personnel needed for the successful result of the commission. | Strength | Continue | Make use of the County personnel available as support staff. Have them prepare and post the agenda, minutes and attachments of the upcoming meetings. Also the budget worksheet and meeting setup, timeliness and protocol of the meetings, The clerk will be the timekeeper and announcer of the meetings.
Personnel - Support Functions | NA | Inman | Personnel | Make county staff 100% assigned to IRC | Weakness | Modify | County staff did a great job supporting IRC. But it seems unfair to make them split their time between IRC and regular county position. Given the demands they faced to meet expectations and aggressive timelines of the IRC they should be 100% IRC.
Personnel - Support Functions | NA | Kristina Kruglyak | Personnel | County Staff | Strength | Continue | Retain as many members of our excellent staff as possible for future redistricting commissions.
Personnel - Support Functions | Bylaws | Sonia Diaz | Personnel | Need to codify IRC’s independence from County of San Diego in bylaws with addition of staff: Executive Director | Weakness | Modify | Amend bylaws to clearly delineate and separate the Independent Redistricting Commission’s (IRC) administrative functions from its mapmaking duties by creating the position of the Executive Director (ED) of the Commission. The ED is not San Diego County staff but an independent, nonpartisan contractor hired by the IRC to take on and manage all hiring and procurement decisions and establish policies and procedures for the functioning of the IRC with final approval of the Commission. Other Commissions have a similar structure (e.g., California Citizens Redistricting Commission, LA County Redistricting Commission, Michigan Citizens Redistricting Commission)
Personnel - Support Functions | NA | David Bame | Personnel | The IRC benefitted from the cost-effective use of County staff whenever possible, including as staff lead. It seemed unnecessary to hire outside staff, such as an Executive Director, to work directly for the IRC. Doubts about staff impartiality & independence seemed resolved by actual work and by the IRC's clarification in revised bylaws. | Strength | Continue | The County should ensure that any county staff working for the IRC have safeguards in place to protect IRC independence from the Board of Supervisors. The Clerk of the IRC should explain requirements and expectations for staff independence at the first full IRC meeting. The IRC, especially officers, should be clear on tasks & deadlines.
Personnel - Consultants - General | Training | Kristina Kruglyak | Doctrine | Ability to Elect Analysis | Weakness | Modify | A group’s (e.g., racial/ethnic) preferred candidate need not identify with that same group. Ability to Elect analysis should be based on all available elections to have a rigorous sample size for decision-making.
Personnel - Consultants - General | NA | David Bame | Doctrine | County staff may have to make some initial decisions on hiring for the IRC during its interim (eight-commissioner) stage, but such decisions cannot prejudge or limit IRC decisions. Initial decisions on hiring of counsel and on county staff support can be clearly explained at the first full IRC meeting, including suggested timelines for decisions. | Threat | Modify | Hiring decisions made by County staff early in the process must be understood, discussed, and formally approved by IRC. Any decisions made to enable initial IRC work, particularly involving legal counsel, should only be made on a contingency basis pending IRC approval or revision.
Personnel - Consultants - General | NA | Christian Grose | Finance | The amount allocated for the RPV statistical consultants did not cover all the many, high quality requests that came in. We ended up doing substantially more work beyond the scope of work identified to be responsive to the Commission's requests. A different consultant may have left the job after finishing SOW only. | Weakness | Modify | The County and the Commission needs to be prepared to allocate more funds for statistical consulting; or have a more discrete set of deliverables (as stated in the scope of work).
Personnel - Consultants - General | NA | Jack Russ | Finance | Outreach consultants and demographic consultants. | Weakness | Modify | The value obtained from the Outreach and Demographic consultants per dollar spent was very disproportionate. Was pleased that we did not increase the Outreach budget late in the whole process.
Personnel - Consultants - General | NA | David Bame | Finance | Sub-contractors proved a somewhat complex challenge in terms of defining what plans & expenditures needed to be shown to the full IRC. The Single Point of Contact system was helpful in this regard, but still left some Commissioners unclear as to what needed to be reported about sub-contractor payments and activities. | Opportunity | Modify | The IRC could work with contractors, either through SPOCs or AHCs, to better define expectations regarding subcontractor funding and activities. While contractors would continue to manage subcontractors, more active IRC consideration would improve public transparency & awareness.
Personnel - Consultants - General | NA | Amy Caterina | Organization | County provided procurement services (DPC). The County procurement process is well established and respected as a best practices process. However, it was a long, time consuming process, fraught with potential for delay. DPC presented a draft RFP to the IRC for approval in December 2020. The IRC created 3 Ad Hoc committees. Final decisions in June. | Weakness | Modify | The new IRC should carefully consider its procurement process for contractors (legal, outreach and demography) with careful attention to going rates for these services and utilization of best practices regarding selection of contractors.
Personnel - Consultants - General | NA | Amy Caterina | Organization | The IRC utilized Single Point of Contract structure to manage its contactors (Demography and Outreach). | Strength | Continue | This process was highly effective.
Personnel - Consultants - General | NA | Elidia Dostal | Organization | County staff has experts on procurement, yet we formed an ad hoc committee for the bidding process for the demographer and public outreach consultants. | Opportunity | Modify | Consider whether County staff is better able to handle procurement rather than an ad hoc committee of the IRC. Because the County has procurement processes (such as bidding and confidentiality) that the IRC must comply with, I believe it is best to allow County staff to handle procurement of the demographer and public outreach consultants.
Personnel - Consultants - General | Budget | Ponds | Organization | Strategic Communication. Outreach and engagement / Public Relations lagged the process, and engaging all elements of SD County communities was incomplete and sporadic. Individual Commissioners providing independent material for publication could prove counter-productive to the IRDC's mission and create a public perception of Commissioner bias. | Threat | Modify | Use performance based contracting. Ensure the process is deliberate, concise, and demanding and ensure discrete SOW line items are included with quantifiable deliverables. Onboard a dedicated journalist to avoid Commissioners creating independent material for publication.
Personnel - Consultants - General | NA | Ponds | Organization | Subject Matter Expert(s): The availability of RPV and VRA SMEs was late in the process and the availability of the experts was challenged by competing requirements. | Weakness | Modify | Onboard VRA, RPV and other specialized subject matter experts during the initial stages of the redistricting process and ensure they are readily available to support the process.
Personnel - Consultants - General | NA | David Bame | Organization | Contractors are necessary to the IRC process, especially for demography and outreach. Early consideration of ideas about contractors, followed by efficient consideration of options and hiring decisions, can help maximize IRC effectiveness throughout its mission. | Opportunity | Modify | No later than the second full IRC meeting, Commissioners should request staff research and options on seeking/hiring/evaluating contractors, including how the IRC will remain in sufficient direct contact with contractor outside of regular meetings (e.g. SPOC).
Personnel - Consultants - General | NA | Kristina Kruglyak | Personnel | Demographer Hiring | Weakness | Modify | Hire demographer earlier.
Personnel - Consultants - General | Mapping Considerations | Kristina Kruglyak | Personnel | Demographer Hiring | Weakness | Modify | Require demographer provide mapping software to commissioners for testing prior to hire. Not a demo of the software, the actual software, so that commissioners can evaluate usability before deciding on which demographer to hire.
Personnel - Consultants - General | NA | Kristina Kruglyak | Personnel | Contractor Hiring | Weakness | Modify | The IRC should be the decision-maker on contracted services; that is not the case if the County process has a committee comprised of 3 voting members from county staff and 2 voting members from the IRC. The County should update this process to be the reverse for any case where the commission is truly supposed to be independent.
Personnel - Consultants - General | NA | Kristina Kruglyak | Personnel | Contractor Hiring | Weakness | Modify | Hire Voting Rights Act Special Counsel earlier.
Personnel - Consultants - General | NA | Kristina Kruglyak | Personnel | Ability to Elect Consultant Hiring | Weakness | Modify | Hire Ability to Elect Consultant earlier.
Personnel - Consultants - General | NA | Kristina Kruglyak | Personnel | Ability to Elect Consultant Hiring | Weakness | Modify | Require proposed statistical process as part of proposal during hiring process for Ability to Elect Consultant.
Personnel - Consultants - General | NA | Ponds | Personnel | Staff Subject Matter Expert(s): Functional staff SMEs in “direct” support of Commissioners in executing their roles and responsibilities as SPOCs and Committee members would improve the effectiveness and efficiency of the IRDC process. | Opportunity | Modify | Identify and assign functional staff SMEs in direct support of Commissioners in executing their duties and responsibilities as SPOCs and Committee members.
Personnel - Consultants - General | NA | Rosette Garcia | Personnel | The 2020 IRC had no procedures in place for procuring outside contractors, and the process used for selecting and hiring outside contractors (via County Procurement Office) was cumbersome, lengthy, and excluded IRC at key decision points. Furthermore, timing of procurements did not provide optimal or timely benefit to the IRC. | Weakness | Modify | Recommend 2030 IRC consider other processes for retaining contractors. Quickly assemble task force to research all options and resolve to hire ALL contractors, especially demographer and expert counsel as early in the timeline as possible. (See other comment about necessity of outside contractor for outreach/comm). Do not wait to hire contractors.
Personnel - Consultants - General | NA | Sonia Diaz | Personnel | Procurement through County of San Diego was burdensome and bureaucratic, leaving the Commission with little autonomy to make hiring decisions for contractors. | Weakness | Cancel | The Commission should no longer depend upon or use the existing County of San Diego Department of Purchasing and Procurement. An Executive Director hired by the IRC to be responsible for these decisions will create autonomy from the County of San Diego and will allow flexibility for the IRC to develop the Scope of Work, Contract, Selection Criteria, and Budget, while maintaining a fair application and interview process administered by the Executive Director.
Personnel - Consultants - General | NA | Arv Larson | Personnel | It was good fortune and sheer luck that a professional demographer was selected as one of the IRC Commissioners. This served to educate the other IRC members of what a demographer is and does, as well as provide invaluable assistance in the selection and oversight of the demographic contractor team. Over the year of working with Ken Inman, I gained the equivalent of a graduate course in applied demography. | Opportunity | Modify | If a demographic professional is not selected as an IRC Commissioner, a professional demographer should be hired to both educate the IRC Commissioners and to act as liaison and interface to the selected demographic contractor.
Personnel - Consultants - Legal | NA | Amy Caterina | Doctrine | County Counsel retained IRC Counsel and signed a long term contract without advising the IRC. County Counsel also amended the contract without informing the IRC in advance. Counsel and County Counsel neglected to provide timely updates to the IRC. | Weakness | Modify | The new IRC should manage its own legal counsel. County Counsel should not be involved in any way. A transition team might assist in process of establishing interim General Counsel. There should be an interim general counsel set up to advise and train the new IRC (as soon as possible).
Personnel - Consultants - Legal | Budget | Amy Caterina | Finance | Legal expenses were significant. | Weakness | Modify | The new IRC needs to take control of its legal expenses as soon as possible. Any early legal contracts should be identified as interim. General Counsel should be established and any Special Counsel and External legal counsel needed should be identified and retained early in the process.
Personnel - Consultants - Legal | Budget | Rosette Garcia | Finance | Budget--legal | Opportunity | Modify | Line item for legal in IRC's budget was by far the highest and, while necessary, costs should be assessed to improve stewardship of county funds. Consider using county staff to provide general (Brown Act/governance) counsel (or outside general counsel at general counsel rates); if possible, contract outside legal counsel only for expert counsel.
Personnel - Consultants - Legal | Personnel - Consultants - General | Sonia Diaz | Personnel | General Legal Counsel for the Commission was initially hired by the County of San Diego and NOT the Commission. Amendments to the 1st contract were not vetted through the Commission and led to much confusion over not only what type of Legal Counsel we had but we were essentially stuck with. IRC was limited to future opportunities to hire Special Counsel late in the map making stage. | Weakness | Modify | At the first meetings of the IRC, the first order of business should be to review and approve the draft RFPs for the Executive Director, General Counsel, and Special Redistricting Counsel. An interim General Counsel could be appointed by the County to facilitate this process but with the understanding that this interim General Counsel will step down once the new legal counsel is hired. A letter of consent must be ratified by the IRC at its first meeting. This written consent is provided under California State Bar’s Professional Rules of Conduct 1.8.6. The consent should occur at or before the time the lawyer has entered into agreement for, charged, or accepted the compensation, or as soon thereafter as reasonably practicable. Since the County pays this counsel before the full IRC is seated, it is an important document that establishes the independence of that counsel and the responsibilities it has to the client, the IRC. Thereafter, the IRC is responsible for hiring its own Legal Counsel and determining however many lawyers are needed to carry out its duties, from development of the redistricting map, to its approval, to handling any potential litigation matters post-approval.
Personnel - Consultants - Legal | NA | Rosette Garcia | Personnel | The contract for general counsel services covered the period from November 2020 through December 2021. The contract's term was set at a time when the map adoption deadline was set for August 15, 2021, allowing for 3.5 months of post-mapping, wrap-up IRC activities. | Opportunity | Modify | When the map adoption deadline was extended to 12-15-21, general counsel services contract should have been extended to accommodate extension, an oversight on the part of, frankly, everyone. The 2030 IRC will need general counsel services 1-2 months beyond deadline and prospectively plan for that, provided by either outside counsel or the County.
Meetings - Execution | NA | Arv Larson | Organization | There seemed to be two levels of IRC meetings - (1) non-public meetings among IRC leadership, COSD-assigned staff, and general counsel and (2) open public meetings involving all IRC Commissioners. These provided no mechanism to involve other Commissioners in the development and practice of necessary processes/procedures/coordination in a non-public venue. The Brown Act restrictions concerning openness of all Commission activities would not apply to the discussion and application of working processes/procedures/coordination necessary to IRC functioning vs. those activities involving actual redistricting information gathering and decision making. Periodic non-public "Executive Session" meetings for these purposes were not held but could have served to make use of individual Commissioner background, experiences, and skills to improve IRC operations. | Opportunity | Modify | Schedule periodic non-public "Executive Session" meetings to give all Commissioners a role in development and application of necessary processes/ procedures/coordination activities.
Meetings - Planning | NA | Amy Caterina | Doctrine | The IRC took a very considerate approach to its doctrine. In retrospect, some decisions on doctrine resulted in delayed actions. For example, early on, the meeting structure was based on a two meeting approach. A topic was raised at the first meeting, discussed and then any action related to the item was addressed in a future meeting. | Weakness | Modify | Decisions were pushed to future meetings and log jams ensued. This approach, while admirable, slowed the business of the IRC, and likely would be unfeasible in a normal (non-Covid delay) IRC. I suggest initial, upfront memo to commissioners with clear analysis & delineated timelines. Share details in advance of meeting notice (full transparency).
Meetings - Planning | Meetings - Execution | Amy Caterina | Doctrine | Chair developed the agenda in coordination with staff and Chair ran the meetings. The current IRC Chair managed the meetings but was unable to participate in the discussion in most cases. | Opportunity | Modify | The new IRC should determine if the appropriate approach to running meetings and determine the most effective path forward. An option would be to hire an Executive Director (or similar title) with experience in running and managing meetings thus freeing up the Chair.
Meetings - Planning | Meetings - Facilities/Logistics | David Bame | Facilities | Planning for IRC public hearing and meeting locations was sufficiently diverse and open, but proved difficult given COVID-19 and other challenges. More specific & directed IRC discussion of predictable requirements (security, bandwidth, seating, hours before closing, etc.) would have yielded greater success. | Opportunity | Modify | IRC officers, staff & outreach contractors could develop an early plan for hearings & meetings locations & requirements, with more regular updates to the full IRC.
Meetings - Planning | NA | Amy Caterina | Material | Meeting materials were provided to the IRC (digitally) and the public on a timely basis. But the printed package didn't always arrive before the meeting. Staff always did an amazing job distributing the meeting materials and other documents, but COVID restrictions hampered distribution of other documents. | Opportunity | Modify | Meeting materials should arrive before the meeting occurs. Blank paper should be provided to Commissioners to print materials as needed. Collateral materials such as posters, business cards, information sheets, handouts and other documents should be made available and provided to Commissioners.
Meetings - Planning | NA | Commissioner Brown | Organization | Overall organization of the commission. | Strength | Continue | Keep a working timeline of the commissions activities and meetings; adjust as needed. A timeline keeps everyone alert of upcoming activities and progress toward the submission of the final map.
Meetings - Planning | Legislation | Inman | Organization | Online meetings were a key reason we succeeded. Online meetings add flexibility for both commissioners and public. They make it much easier to move quickly and effectively give everyone more ability to participate. | Strength | Modify | Make it possible for commission to use online meetings to conduct business.
Meetings - Planning | Public Outreach | Arv Larson | Policy | A large majority of COSD voters lives in the western third of the County. Nearly half of COSD voters live in the City of San Diego. While IRC open in-person meetings and public hearings were necessarily limited due to pandemic concerns, there were relatively few meetings held within San Diego City or COSD coastal regions. Nearly all such meetings were held east of the I-5 with the exception of those held in the County Administrative Building on Harbor Drive. Meeting venue locations did not seem to match COSD population distribution. | Weakness | Modify | IRC open meetings and public hearings should be held in appropriate venue locations more directly reflecting voter population distributions. There should be more such meetings in all regions of San Diego City and COSD coastal areas.
Meetings - Planning | NA | Rosette Garcia | Policy | Due to the COVID-19 pandemic, the IRC was required to meet virtually over Zoom. | Opportunity | Continue | While initially awkward, over time Commissioners became more comfortable with the Zoom format. Zoom meetings may be more efficient and productive and I would urge the 2030 IRC to continue meeting virtually especially for working groups, committees, etc. I do not recommend completely eliminating in-person meetings, however.
Meetings - Facilities/Logistics | NA | Amy Caterina | Facilities | County facilities were made available to the IRC. COVID protocols impacted our ability to meet in person for the first nine months or so. | Strength | Modify | The IRC did not have a home and some space should be dedicated to the new IRC.
Meetings - Facilities/Logistics | NA | Arv Larson | Facilities | Many of our open in-person meetings and public hearings were held in COSD facilities, including several in the County Administration Building in spaces adjacent to the Board of Supervisors administrative chambers. Our use of these COSD facility venues tended to give the impression that our proceedings were part of the COSD political structure and our IRC activities were not really independent from the control by the COSD political incumbents. | Opportunity | Modify | Hold all IRC open meetings and public hearings in non-COSD facilities such as public or private meeting halls/auditoriums (e.g., San Diego City Marina Conference Center) , school auditoriums, or city/COSD library facilities.
Meetings - Facilities/Logistics | NA | Commissioner Brown | Facilities | Locations and facilities of special and public meetings. | Strength | Continue | Virtual and in-person meetings should be arranged for all meetings for the public and the Commission. Meetings are available to many more attendees when providing the venue in many different access points.
Meetings - Facilities/Logistics | Public Feedback | Sonia Diaz | Material | Meeting minutes and video recordings of meetings documented thoroughly all activities and was made publicly available. Public was able to submit public testimony in multiple ways. | Strength | Modify | For live call-in testimony provide a call back number for those waiting in the cue to get a text message when they are about to be called on.
Meetings - Facilities/Logistics | NA | Ponds | Policy | Alternative IRDC Meeting Options. The flexibility, safety, security, and peace of mind afforded by teleconferencing was significant. | Strength | Continue | Continue to include alternative meeting options to support redistricting.
Meetings - Execution | NA | Kristina Kruglyak | Organization | Meeting Length | Weakness | Modify | Meetings should be timebound and few if any should go above 3 hours. Between bi-monthly meetings that are 8hrs long or weekly meetings that are 3 hours long, the latter is better and would lead to overall improved productivity.
Meetings - Execution | NA | K. Elliott | Policy | Meeting times ran very long which makes it difficult for staff, IRC and public to remain engaged. We have worked with other municipalities who in order to keep their meetings running on time had a policy requiring voting members to vote (first, second, pass) to extend the meeting in 15-minute increments. | Opportunity | Modify | This requirement helped the independent commissioners to keep track of and budget their time very closely instead of having to vote to increase the meeting every 15 minutes. Something to consider.
Meetings - Execution | Public Feedback | Commissioner Brown | Training and Education | Public Education Meetings. Participation, number and General Info. | Strength | Continue | Difficulties managing length of meetings. Allow 1 min per person, 3 minutes per group of 3, double if translation needed. Post rules in each agenda notes. Hold at least one public meeting is each district. Virtual and in person are preferred.
Public Outreach | NA | Commissioner Brown | Material | Field Presentations to Public Groups | Strength | Continue | Have different presentations available for various timing venues. 15, 30 and 45minute presentations. Have education tour presentations virtually to public by district. Same presentation but highlighting each districts map.
Public Outreach | NA | David Bame | Material | An earlier IRC commitment to review proposed materials with staff and contractors during meetings could build IRC effectiveness and Commissioner participation in outreach. | Weakness | Modify | The IRC should consider at least two in-depth discussions (during the pre-mapping and mapping phases, respectively) of materiel prepared for public outreach. The IRC could use these discussions to refine messaging and seek new, targeted outreach to increase participation by hard-to-reach County residents.
Public Outreach | Personnel - Consultants - General | Kristina Kruglyak | Personnel | Public Outreach | Weakness | Modify | The consistent feedback from East County was that limited internet availability meant they did not know about the redistricting process early on. Demographers should be aware of internet availability across the County and address outreach accordingly.
Public Outreach | NA | Arv Larson | Policy | In my various non-IRC informal interactions over 2021 (with friends, associates, and assorted members of the public) I sensed confusion and limited knowledge from this slice of the voting public about County districting much less redistricting. There seemed to be little understanding of why any of this mattered in their day-to-day lives. More to the point, in the countless public input both electronic and verbal over the course of our outreach, few submissions went beyond stating that some change/issue was desired or not desired but did not usually address why the submitter felt that way about what district they lived in and how it would impact their lives if change or no change occurred. Much of our public input seemed to come from various special-interest groups and their supporters. Our briefing materials as developed did not address why COSD districts mattered except to state that the Board of Supervisors controlled a multi-billion dollar budget which served to provide certain services that seemed mostly County-wide and not specific to any one COSD district. | Weakness | Modify | The IRC must develop a credible rationale for why COSD districts matter to the individual voter beyond keeping organizational units (cities, communities, etc.) whole within a given district and not to divide identified COIs among districts to the extent possible. But it is usually not clear why this matters to the individual voter in a tangible way (e.g., better schools, improved traffic, better policing, more public recreation, etc.). Our briefing and publicity material should give a compelling rationale for why COSD districts matter beyond that we are a big County with a big budget. We should request that submitted public comment specifically tell us why COSD districting and district boundaries really impact their personal lives and convenience.
Public Outreach | NA | Arv Larson | Policy | Although the IRC received a tremendous outpouring of public input and press accounts of our activities, most of the COSD voters I encountered who were not otherwise engaged in this process knew little if anything about our redistricting efforts. One estimate would be that more than 98% of COSD voters did not hear our messages or know of our activities. Clearly our public outreach and general attendance in our public meetings and hearings by more voters other than those connected with special-interest groups could be improved. | Weakness | Modify | Develop more effective means of communicating to the general COSD voting public who we are, what we do, and why it matters to them. Our message seems to get through to various special interest groups who can then direct their membership to communicate with us re their special interest concerns. The general public has equal interests in redistricting outcomes, but they must first be made aware of how redistricting practically effects them and the importance of letting us know how they feel. This can be done with a more extensive (and expensive) public outreach campaign.
Public Outreach | NA | Arv Larson | Policy | It is either unknown or confusing to most members of the COSD public that there are at least three IRCs operating within the County. The individual IRCs at the State, County, and local level generally have the same message, use the same census data, and desire input from the same voting public. In most cases, each IRC is breaking new ground in 2021 as the first to exercise true independence from past redistricting (and political) practices. To date there have been mostly limited attempts for coordination and cooperation among these three levels of IRCs. | Opportunity | Modify | Prior to the next redistricting cycle in 2030, develop a policy among each of the relevant IRCs serving to improve coordination and cooperation for mutual benefit. For example, initial information presentations to public groups could jointly present the State, County, and local redistricting stories to include descriptions of current districts, the desire/need for public input, and the how/why of redistricting processes. The public hearings conducted by each IRC could on occasion be held jointly and receive joint testimony re often overlapping voter concerns and desires.
Public Outreach | NA | David Bame | Policy | Community Planning Groups, tribes, and other organizations sometimes expressed unawareness of the IRC's work late in the IRC's mapping process. While a fair number of such groups were contacted directly during outreach activities, a more focused approach might have inspired increased awareness. | Opportunity | Modify | The IRC should consider contacting all CPGs, tribes, and similar groups before and during pre-mapping public hearings to encourage attendance and participation in IRC hearings and meetings. The IRC may wish to send regular updates, including links to draft maps, to as many such bodies as possible during the mapping (DMPH) phase.
Public Outreach | NA | Commissioner Brown | Training and Education | Public Education | Strength | Continue | Most of the public is not aware that there are redistricting commissions for the State, County, Local governments. All working on maps independently but simultaneously. Each commission draws a different map for a different purpose. Good idea to tell the public in your general education tour.
Mapping Considerations | NA | Kristina Kruglyak | Doctrine | Mapping | Opportunity | Modify | Informal mapping process should begin based on interim data (both in terms of the non-final data itself, and also based on the less-user-friendly data format) and not be gated by final data cleanup, which has minimal impact on final population values.
Mapping Considerations | NA | Kristina Kruglyak | Doctrine | Mapping | Opportunity | Modify | Require each commissioner to draft own maps. First based on public testimony alone, then after additional testimony on specific draft maps. Seeing all commissioners’ maps will allow for easier identification of shared priorities and key differences that can be easier addressed with the map as a visual aid rather than just by verbal descriptions.
Mapping Considerations | Training | Kristina Kruglyak | Doctrine | Mapping | Weakness | Cancel | Do not make decisions on a district-by-district basis. All commissioners should understand that every single decision for one district has a significant impact on every other district. Making decisions for a single district without seeing the resulting map as a whole leads to bad maps.
Mapping Considerations | NA | Kristina Kruglyak | Doctrine | Mapping | Threat | Modify | Any map received should be considered as a COI map unless it covers the entirety of the County. If an individual or a group submits a proposed single district map, then that map should only be considered as COI, and should not be considered as a draft map.
Mapping Considerations | NA | David Bame | Facilities | Mapping software and inputs were hard to encourage from the public at various points. With presumably more time available for the next IRC, earlier "mapping outreach" (even before census data is received) at higher education campuses or community centers in each district could encourage more robust & earlier submissions. | Opportunity | Modify | Early IRC attention to demography software could be helpful to ensuring maximum public contributions. The IRC could consider mapping workshops in each district, specifically aimed at using latest technology to show how maps could be drawn & submitted, even before census data is received.
Mapping Considerations | NA | Jack Russ | Organization | The Ad Hoc committees worked well in getting work done expeditiously. | Opportunity | Modify | During the initial map drawings, it may would have been beneficial if each of the 5 Districts commission members form an ad hoc to draw maps of what they would think their respective districts should look like. The resultant conjoined map would be a good starting point.
Mapping Considerations | Training | K. Elliott | Organization | FLO’s original plan was to train the IRC to use the DSM to create their own district maps. After training was completed, feedback from IRC members indicated that creating maps themselves was not ideal. FLO created the Springboard maps and then created subsequent district maps based on feedback received from the IRC during the public meetings. | Opportunity | Modify | The process to reach the final maps took much longer than originally anticipated and caused a bit of a rush at the end. The recommendation is to have more training on the DSM so IRC feel confident to create maps, or start the mapping process earlier to allow for additional time to reach the final map.
Mapping Considerations | NA | Kristina Kruglyak | Organization | Mapping | Weakness | Cancel | Do not use springboard maps. They confuse the public (and the commissioners); the only springboard map should be the existing district boundaries (and even this map should not be referred to a springboard map).
Mapping Considerations | NA | Rosette Garcia | Organization | Throughout the mapping process, commissioners received, processed and developed ideas about mapping completely in isolation from one another. The only opportunity to discuss principles, priorities, or even COI data was in full meetings, often with very strict timing requirements. | Weakness | Modify | Consider small working groups to discuss and process information and especially to level-set among comm'rs understanding of COI data, mapping process, and ideas for line drawing (responding to COI input and Census data). Working group meetings can be streamed live via zoom &/or recorded for transparency.
Mapping Considerations | NA | Rosette Garcia | Policy | During the mapping process, draft maps numbering system, color coding and district numbering system was confusing. Terminology for districts also led to misperceptions and perhaps unconscious bias. (don't know if this is policy or organization or what category). | Weakness | Modify | Recommend IRC spend time in advance determining numbering system to be used. Maintain map numbers as they evolve (revised map 1 becomes map 1a rather than map 4, e.g.). Use letters for district numbers in all cases, rather than nicknames or #s, and use consistently from map to map (east county district is always Dist E, e.g).
Mapping Considerations | NA | Rosette Garcia | Policy | During mapping process, the IRC embraced a clean slate approach and did not consider using existing (2010) supervisorial map as a starting point, revising it in response to COI input (and we did have input requesting no change to the map or stating that they liked their district as currently drawn). | Opportunity | Modify | Recommend that 2030 IRC spend some time reviewing 2021 map, assessing its strengths and weaknesses, and considering revising it rather than starting with a blank slate. (Avoid bias towards blank slate approach.)
Public Feedback | NA | Kristina Kruglyak | Doctrine | Public Feedback | Weakness | Cancel | Group comment was severely taken advantage of to get longer speaking time. A group should have a very constrained definition if they are given a longer time to speak.
Public Feedback | NA | Rosette Garcia | Material | I found it very difficult to keep track of the public input we received, especially community of interest (COI) data. The emails required each comment be opened separately and the Excel worksheet where everything was compiled was not user friendly. The methods for compiling, tracking and distributing Public/COI input should be improved. | Weakness | Modify | Receiving the public input in one long document, as we did at the end of the process, was much simpler and easier than prior method. Staff/demographers must develop a method that will allow comm'rs to keep track of COI data BY TYPE/COI in an ongoing way so that comm'rs can review that easily/quickly as it is essential to mapping decisions.
Public Feedback | NA | Kristina Kruglyak | Organization | Public Feedback | Weakness | Modify | Written public comment should be better consolidated in terms of readability; even merging all of the comments into a single PDF packet would be easier than having hundreds of separate PDF files.
Public Feedback | NA | Kristina Kruglyak | Organization | Public Feedback | Opportunity | Modify | Ideally sentiment analysis software (based on natural language processing/text mining) could be used to synthesize written feedback and merge de-facto-identical comments so that the commissioners can review the comment and then understand how many individuals provided that same sentiment.
Public Feedback | NA | Kristina Kruglyak | Organization | Public Feedback | Weakness | Modify | Public feedback should not be open-ended but should be guided by questions so that the responses are more usable to commissioners. This process could start by asking the user to submit feedback on a particular topic and then provide a set of guiding questions. See Appendix for example. Appendix: Example Topics for user to select when submitting feedback: * COI Testimony * Draft Map Feedback * Commission Software Feedback * Past Agenda Item (non-Map) * Upcoming Agenda Item (non-Map) Example Form Questions if user selected Draft Map Feedback from the above list: * Where do you live? (Drop-down) * What is your preferred map? (Drop-down) * What is your least preferred map? (Drop-down) * What feature(s) do you like about your preferred map? (Checkbox plus ‘Other’ to allow for user entry) * How could your preferred map be improved? (Checkbox plus ‘Other’ to allow for user entry) * Any additional comments (Open field) The above structure would allow for easy quantitation of preferred maps as a function of district/locale. Similar benefits could come from having such a structure for the other topics.
Public Feedback | NA | Kristina Kruglyak | Organization | Public Feedback | Weakness | Modify | Hearing verbatim feedback in meetings is not value-add for the commission or the public. It would be better if attendees could up-vote messages live so that everyone can immediately see the quantifiable level of support for a given point rather than sporadic reiteration. This would also allow more objective comparison of feedback across meetings.
Public Feedback | NA | Jack Russ | Policy | Taking testimony from the public was overly time consuming, especially when the input had obviously been coordinated and were "carbon copies" of each other. | Weakness | Modify | Have individuals identify themselves as a group and have one group spokesman provide testimony. The time allotted for such a group presentation could be longer than 3 minutes. Hearing the same testimony over-and-over again takes time away from others who may have different issues.
Public Feedback | Mapping Considerations | David Bame | Policy | Various Commissioners & members of the public claimed that the IRC accepted some public input on maps at face value, without extensive analysis of whether such inputs might limit IRC options about other locations. Commissioners and IRC leadership asked questions about such input publicly & repeatedly, but claims of unintended effects continued. | Weakness | Modify | The IRC should establish a process to regularly and explicitly review all public inputs, especially on maps, to further make clear that nothing is accepted as is. One possibility would be to instruct the IRC demographer to provide routine updates on which inputs from the public might deserve review or reconsideration.
Closeout & Transition | NA | Amy Caterina | Doctrine | Commissioners did not always make initial decisions regarding various aspects of doctrine. Others made decisions before commissioners were sworn in which often could not easily be reversed. There was not a lot of direction provided in the law and as a result early actions were taken without input from the commissioners. | Opportunity | Modify | Establish a transition team to assist the next IRC. Have analysis and options prepared for the new IRC. Any initial decisions have to be established as interim in order for the new IRC to choose a path that best fits their composition and outlook.
Closeout & Transition | NA | Christian Grose | Organization | I wanted to praise the Commissioners, the staff, Marguerite, FLO, and other key principals for what was done. I would caution that 'lessons learned' not be that future commissions should adopt a more top down approach. The give and take from many Commissioners, staff, the public via public input and public comments, etc. made the process better. | Strength | Continue | I would continue to make sure there are multiple outlets for a variety of inputs from many key players and the public. The key advantage of an independent commission, even though it can be a bit less manageable and more unwieldy, is that many inputs come in from multiple places. Retain and maintain the ability to take public inputs.
Closeout & Transition | NA | Ponds | Organization | Redistricting Commission Advisory Group (R-CAG). Future IRDC would benefit from the education and experience of prior Redistricting Commissioners to design, develop, plan and execute the IRDC project. In coordination with the Staff, the R-CAG would collaborate directly with the IRDC executing their established roles and responsibilities. | Opportunity | Modify | Explore the options, opportunity, and feasibility of establishing a Redistricting Commission Advisory Group (RCAG) and provide the results of the findings to the appropriate governing agency --- The San Diego Association of Governments, County Board of Supervisors --- for final determination.
Closeout & Transition | NA | Ponds | Organization | Continuity of Operations / Succession Plan. The IRDC did not have a continuity of operations and succession plan to respond to organizational disruptions, minimize impact and ensure operation continuity and resiliency. | Threat | Modify | Explore the options and opportunities and feasibility of establishing a continuity of operations and succession plan, including a pool of Alternate Commissioners. Alternate Commissioners would be identified during the selection process, receive requisite training requirements, and attend all meetings to be immediately ready serve when required.
Closeout & Transition | NA | Amy Caterina | Policy | The IRC and Staff developed operating policies. | Opportunity | Modify | A full Standard Operating Procedure manual should be developed to hand off to the new IRC.
Closeout & Transition | NA | Rosette Garcia | Training and Education | Lessons Learned web form was cumbersome and made the process of submitting lessons learned inefficient and time consuming. Categories were unclear, should be re-examined, some deleted and others added. Very limited space for explanation--often unable to fully explain a lesson learned, provide context or rationale for the recommendation. | Opportunity | Modify | Consider another format for lessons learned and begin compiling earlier. Research possibility of adhoc comm compiling submissions without violating Brown Act. Add categories for Mapping, Committees, Legal, Contractors. Combine some topics into one category (Policy/Doctrine/Bylaws). Clarify topics under each category.

## Recommend (hidden)
Recommendation
Decisions were pushed to future meetings and log jams ensued. This approach, while admirable, slowed the business of the IRC, and likely would be unfeasible in a normal (non-Covid delay) IRC. I suggest initial, upfront memo to commissioners with clear analysis & delineated timelines. Share details in advance of meeting notice (full transparency). | 1
Establish a transition team to assist the next IRC. Have analysis and options prepared for the new IRC. Any initial decisions have to be established as interim in order for the new IRC to choose a path that best fits their composition and outlook. | 2
The IRC should decide the organizational structure in respect to its doctrine and choose the structure that is most appropriate. An executive external to the county system might be beneficial as a spokesperson and overall outreach coordinator. | 3
The new IRC should manage its own legal counsel. County Counsel should not be involved in any way. A transition team might assist in process of establishing interim General Counsel. There should be an interim general counsel set up to advise and train the new IRC (as soon as possible). | 4
The new IRC should determine if the appropriate approach to running meetings and determine the most effective path forward. An option would be to hire an Executive Director (or similar title) with experience in running and managing meetings thus freeing up the Chair. | 5
All voices are important. Commissioners should be representative of the entire county. Maps should be drawn without influence for political gain. The commission should follow the Voter's Rights Act, Bylaws, US and State Constitution requirements keeping in mind the Communities of Interest's requests to stay intact. | 6
Further refine, through IRC discussion and vote, agreed guidelines and limits in Elections Code and IRC Bylaws on Commissioner participation in political party meetings & events, disclosure of contacts with political actors (including those outside formal parties), and other such political activity. | 7
Hiring decisions made by County staff early in the process must be understood, discussed, and formally approved by IRC. Any decisions made to enable initial IRC work, particularly involving legal counsel, should only be made on a contingency basis pending IRC approval or revision. | 8
-Apply 9-vote requirement only to mapping/major decisions, & 8 votes on admin/hiring decisions -keep periods b/w receipt of SWDB data & final map approval, & b/w IRC’s first map and final map, regardless of census delays -consider 7-work day period b/w release and approval of final map, for ROV and other requests for technical changes | 9
Perhaps amend bylaws to clarify clearly that commissioners do not represent their districts, but are instead expected to combine their knowledge of a given district with the knowledge of their colleagues. | 10
Do not make decisions on a district-by-district basis. All commissioners should understand that every single decision for one district has a significant impact on every other district. Making decisions for a single district without seeing the resulting map as a whole leads to bad maps. | 11
Group comment was severely taken advantage of to get longer speaking time. A group should have a very constrained definition if they are given a longer time to speak. | 12
Informal mapping process should begin based on interim data (both in terms of the non-final data itself, and also based on the less-user-friendly data format) and not be gated by final data cleanup, which has minimal impact on final population values. | 13
Require each commissioner to draft own maps. First based on public testimony alone, then after additional testimony on specific draft maps. Seeing all commissioners’ maps will allow for easier identification of shared priorities and key differences that can be easier addressed with the map as a visual aid rather than just by verbal descriptions. | 14
Any map received should be considered as a COI map unless it covers the entirety of the County. If an individual or a group submits a proposed single district map, then that map should only be considered as COI, and should not be considered as a draft map. | 15
A group’s (e.g., racial/ethnic) preferred candidate need not identify with that same group. Ability to Elect analysis should be based on all available elections to have a rigorous sample size for decision-making. | 16
Commissioners claim an ability to be impartial, a point that deserves equal emphasis and commitment, to avoid even the appearance of bias as well as commissioners acting as a member of, or an advocate for, a COI or other group. (This could also be a training item, to include pointing out that commissioners do not "represent" their district) | 17
Start recruitment early – at least one year before the next redistricting cycle (2029) - an aggressive community outreach to recruit diverse body of applicants utilizing a variety of methods via television/radio PSA, e-list servs, print and digital ads on social media. Publicize at existing community venues/groups: o CBOs and volunteers already engaged in Census outreach o Community Planning Groups o Town Council Meetings o PTA meetings o Places of worship o Recreation centers and libraries Civic engagement clubs at community colleges and universities | 18
The deadline for applications should be moved to spring (March/April) with an application review period moved up at least one to two months earlier. This would have the final 60 applicants that move onto the lottery stage happen in June so that the supervisorial meeting to select the first 8 can occur in August with the first IRC meeting to happen in September/October instead of November. | 19
The IRC did not have a home and some space should be dedicated to the new IRC. | 20
Hold all IRC open meetings and public hearings in non-COSD facilities such as public or private meeting halls/auditoriums (e.g., San Diego City Marina Conference Center) , school auditoriums, or city/COSD library facilities. | 21
Virtual and in-person meetings should be arranged for all meetings for the public and the Commission. Meetings are available to many more attendees when providing the venue in many different access points. | 22
IRC officers, staff & outreach contractors could develop an early plan for hearings & meetings locations & requirements, with more regular updates to the full IRC. | 23
Early IRC attention to demography software could be helpful to ensuring maximum public contributions. The IRC could consider mapping workshops in each district, specifically aimed at using latest technology to show how maps could be drawn & submitted, even before census data is received. | 24
County staff should prepare in advance so that all equipment is procured and ready to distribute from the day that commissioners are selected, including clear process for how materials will be delivered. | 25
The IRC should receive the final financial update from staff with detailed expenses (including the final County outlay for staff and various resources (total staff salaries, any DPC , County Counsel and County Communications expenses incurred). The IRC needs to know the total amount expended. The new IRC should decide who manages finances. | 26
The new IRC needs to take control of its legal expenses as soon as possible. Any early legal contracts should be identified as interim. General Counsel should be established and any Special Counsel and External legal counsel needed should be identified and retained early in the process. | 27
This situation is codified in the law, but many commissioners put in excessive time and should be compensated, similar to State CRC, although maybe not at the same level. A transition team could reach out to the legislators and ask to have this considered for all Independent Redistricting Commissions. | 28
Appoint an IRC Commissioner to serve as Treasurer and establish a regular Budget committee for oversight of all IRC financial activities. Establish a working budget early on, revise as necessary as anticipated costs become clearer, and obtain additional funding resources from the BOS early in the redistricting cycle. Provide bi-monthly budget reports to the IRC. | 29
The County and the Commission needs to be prepared to allocate more funds for statistical consulting; or have a more discrete set of deliverables (as stated in the scope of work). | 30
1. Get budget upfront for the commission from the County. 2. Have County staff prepare and present the monthly budget at the last commission meeting of each month. 3. Gives Commission a guideline for expected upcoming Request for Proposal expenses and miscellaneous expenses. | 31
The IRC, perhaps working from a Budget AHC, should approve a sufficiently detailed budget in its first month of work. A Legal Budget AHC should also be considered. The IRC also should plan early for any possible supplemental request, to ensure such a request is made only once to address all budget requirements. | 32
The IRC could work with contractors, either through SPOCs or AHCs, to better define expectations regarding subcontractor funding and activities. While contractors would continue to manage subcontractors, more active IRC consideration would improve public transparency & awareness. | 33
The value obtained from the Outreach and Demographic consultants per dollar spent was very disproportionate. Was pleased that we did not increase the Outreach budget late in the whole process. | 34
Revise FMB policy, protocols and processes to include Commissioners in the initial stages of design, development and execution, including a discretionary fund line item to allow Commissioners the flexibility and agility to respond to short notice and unforeseen requirements. | 35
Recommend 2030 IRC consider using County staff for outreach/communications as they have considerable existing resources/staff that would likely result in more efficient/effective/fiscally prudent processes and deliverables, AND make available more funding for demographer consultant, a high priority for resource allocation. | 36
Line item for legal in IRC's budget was by far the highest and, while necessary, costs should be assessed to improve stewardship of county funds. Consider using county staff to provide general (Brown Act/governance) counsel (or outside general counsel at general counsel rates); if possible, contract outside legal counsel only for expert counsel. | 37
See comment above about establishing Budget Subcommittee | 38
The structure is reasonably sound, but expanding the executive team could be advantageous. A rotating chair could help reduce burnout and even out the workload over the redistricting period. Identifying an individual spokesperson would reduce the load on the Chair. | 39
Appoint an ad hoc committee to schedule and organize a series of non-business gatherings such as a potluck lunch or dinner in public or private spaces. All IRC and staff would be invited but with no pressure to attend. Also schedule occasional all-IRC "Happy Hour-type" social gatherings somewhere with free parking. All participants in these activities would understand to be careful to avoid any Brown Act violations. | 40
Two Co Chairs help balance the workload of the Chairperson. Point of Contact with the large contractors helps keep the commission aware of progression and problems. Ad hoc committees eliminated the public notice constraints brought on by the Brown Act. Small committees with a specific purpose disbanded when the purpose was accomplished. | 41
The interim IRC should choose an interim chair & vice-chair to serve until at least the 3rd full IRC meeting, allowing Commissioners to consider best long-term options. Chairs & vice-chairs may need to spend up to 15 hours/week on IRC work. Officers should decide on how active they will participate in IRC discussions, and so inform the IRC. | 42
The IRC could develop a more specific, targeted plan for Commissioners to seek and fulfill leadership opportunities, especially in sharing ad hoc committee work, to foster more effective participation and contributions to the full IRC's work. | 43
Possible rotate chairing meetings between the elected officers. Different modes of leadership could possible change the character of the conversation which was mostly many micro-monologues. | 44
Maintain single Chair. This allows for continuity and uniformity. | 45
Continue to utilize committees to support the IRDC process, ensuring that each and every Commissioner have an opportunity or are assigned to a committee based on expertise and experience. | 46
Maintain the Chair and Co-chair construct and establish a process to rotate Co-chairs into the Chair position to ensure workload balance and continuity. | 47
I recommend rotating officers, allowing for more than one person to serve as chair, even allowing/planning for new officer elections throughout process to encourage parity of influence among 14 comm'rs. (would require bylaws amendment). | 48
Update the Bylaws to provide clearly defined and specific responsibilities for all Executive Officer positions and require that there be partisan balance (e.g., two Co-Chairs representing each party). The ideal structure would be the following: Two Co-Chairs, Secretary, Parliamentarian, and a Treasurer. Ideally, each of the five officers elected represent a different supervisorial district. The Co-Chairs will share the responsibility of conducting meetings, developing the meeting agenda, inviting guest speakers where appropriate, and ensuring that deliberations from both the general public and Commissioners go as smoothly as possible during meetings. The Secretary would work with County Staff (Clerk of the Board of Supervisors) to ensure that the meeting minutes are accurate, will assist Chairs with the creation of the agenda, assist in community outreach for special projects (e.g., education tours, design of external-facing flyers of the Commission, proposal of new meeting venues, etc.). The Parliamentarian must be present at all meetings and will advise on parliamentary procedure, in consultation with General Counsel, and recommends amendments and updates to the Bylaws to the Commission. The main role of the Parliamentarian is to support the Co-Chairs during each meeting to ensure smooth flow of meetings (a lot of this work is already done by the Clerk but will support this role, especially managing public testimony as the meetings are heavily attended toward the end). The Treasurer chairs the Budget Subcommittee and is the Commission liaison for all budgetary matters before the Commission; this includes submitting formal requests (with Commission approval) to the Board of Supervisors. After the monthly budget report is approved by the Budget Subcommittee, the Treasurer reads and presents the report during the regular Commission meetings. | 49
Amend Bylaws to allow for, at a minimum, the creation of the following standing Committees: o Budget and Oversight – Chaired by the Treasurer of the IRC. Reviews all expenditures of the Commission and make recommendations for new expenditures; develop and approve a monthly expenditure report to the full Commission at regular meetings. Review and approve salaries for all contractors and subcontractors, contracts, and review of pro formas, and maintain a full public record of receipts for work rendered. o Community Outreach & Engagement – In collaboration with the Executive Director, develop a public outreach and engagement plan to be approved by the IRC. Provide ongoing support and direction to the Executive Director on venues for meetings Bylaws, and Community Outreach. Each of these meetings will require to adhere to the Brown Act and must post public agendas and hold their meetings in public. | 50
Meeting materials should arrive before the meeting occurs. Blank paper should be provided to Commissioners to print materials as needed. Collateral materials such as posters, business cards, information sheets, handouts and other documents should be made available and provided to Commissioners. | 51
computers were managed through an external provider. Commissioners were not set up under the County IT program (for external computer use and support) and as a result Commissioners faced work interruptions, delays and other inconveniences. The new IRC computers should be set up with the same parameters as county employees. | 52
Have different presentations available for various timing venues. 15, 30 and 45minute presentations. Have education tour presentations virtually to public by district. Same presentation but highlighting each districts map. | 53
The IRC should consider at least two in-depth discussions (during the pre-mapping and mapping phases, respectively) of materiel prepared for public outreach. The IRC could use these discussions to refine messaging and seek new, targeted outreach to increase participation by hard-to-reach County residents. | 54
IRC staff should work earlier (e.g. by the 3rd full IRC meeting) and more often with IT staff on IRC-approved IT tasks, including access to mobile devices; "fenced-off" periods, especially during mapping, with software updates to occur before or after such periods; and a clear retention policy for IRC emails and documents. | 55
One recommendation is to have a separate "Materials" webpage to host all relevant materials all in one place for the IRC members to easily access. This could be linked to each agenda to remind IRC members and the public where to find these helpful materials. | 56
Identify and deliver IT resources to Commissioners during the initial stage of the redistricting process. | 57
Receiving the public input in one long document, as we did at the end of the process, was much simpler and easier than prior method. Staff/demographers must develop a method that will allow comm'rs to keep track of COI data BY TYPE/COI in an ongoing way so that comm'rs can review that easily/quickly as it is essential to mapping decisions. | 58
For live call-in testimony provide a call back number for those waiting in the cue to get a text message when they are about to be called on. | 59
This process was highly effective. | 60
Towards the end of the process, there was an uneven workload balance. The IRC should consider modifying the bylaws to establish a rotating Chair or Co-Chair scenario. The role of the Spokesperson should be more clearly defined and perhaps allocated to one individual as to reduce the workload of the Chair. | 61
The new IRC should carefully consider its procurement process for contractors (legal, outreach and demography) with careful attention to going rates for these services and utilization of best practices regarding selection of contractors. | 62
The new IRC should be composed of a similar group of commissioners as much as possible. Aggressive advance promotion of the new IRC in each of the five districts will help insure that there is a great base of candidates from all five districts from which to choose. The transition team could facilitate. | 63
Following the independent selection of IRC membership, the IRC should solicit and hire an Executive Director, support staff, and outside general counsel. The COSD BOS should fund this effort but otherwise be uninvolved with IRC organizational and operational activities. | 64
Schedule periodic non-public "Executive Session" meetings to give all Commissioners a role in development and application of necessary processes/ procedures/coordination activities. | 65
For the future, it may be helpful for the Commission to receive VRA/RPV training much earlier. The CA state commission did that. | 66
I would continue to make sure there are multiple outlets for a variety of inputs from many key players and the public. The key advantage of an independent commission, even though it can be a bit less manageable and more unwieldy, is that many inputs come in from multiple places. Retain and maintain the ability to take public inputs. | 67
Keep a working timeline of the commissions activities and meetings; adjust as needed. A timeline keeps everyone alert of upcoming activities and progress toward the submission of the final map. | 68
Continue to ensure the goals, authorities, and limitations of ad hoc committees are clearly understood by all Commissioners and the public, including through holistic summaries and updates of AHC work and through clearly defined tasks from the full IRC. | 69
No later than the second full IRC meeting, Commissioners should request staff research and options on seeking/hiring/evaluating contractors, including how the IRC will remain in sufficient direct contact with contractor outside of regular meetings (e.g. SPOC). | 70
Consider whether County staff is better able to handle procurement rather than an ad hoc committee of the IRC. Because the County has procurement processes (such as bidding and confidentiality) that the IRC must comply with, I believe it is best to allow County staff to handle procurement of the demographer and public outreach consultants. | 71
Start commission in August to give them 12 months. | 72
Make it possible for commission to use online meetings to conduct business. | 73
During the initial map drawings, it may would have been beneficial if each of the 5 Districts commission members form an ad hoc to draw maps of what they would think their respective districts should look like. The resultant conjoined map would be a good starting point. | 74
The process to reach the final maps took much longer than originally anticipated and caused a bit of a rush at the end. The recommendation is to have more training on the DSM so IRC feel confident to create maps, or start the mapping process earlier to allow for additional time to reach the final map. | 75
Do not use springboard maps. They confuse the public (and the commissioners); the only springboard map should be the existing district boundaries (and even this map should not be referred to a springboard map). | 76
Meetings should be timebound and few if any should go above 3 hours. Between bi-monthly meetings that are 8hrs long or weekly meetings that are 3 hours long, the latter is better and would lead to overall improved productivity. | 77
Written public comment should be better consolidated in terms of readability; even merging all of the comments into a single PDF packet would be easier than having hundreds of separate PDF files. | 78
Ideally sentiment analysis software (based on natural language processing/text mining) could be used to synthesize written feedback and merge de-facto-identical comments so that the commissioners can review the comment and then understand how many individuals provided that same sentiment. | 79
Public feedback should not be open-ended but should be guided by questions so that the responses are more usable to commissioners. This process could start by asking the user to submit feedback on a particular topic and then provide a set of guiding questions. See Appendix for example. Appendix: Example Topics for user to select when submitting feedback: * COI Testimony * Draft Map Feedback * Commission Software Feedback * Past Agenda Item (non-Map) * Upcoming Agenda Item (non-Map) Example Form Questions if user selected Draft Map Feedback from the above list: * Where do you live? (Drop-down) * What is your preferred map? (Drop-down) * What is your least preferred map? (Drop-down) * What feature(s) do you like about your preferred map? (Checkbox plus ‘Other’ to allow for user entry) * How could your preferred map be improved? (Checkbox plus ‘Other’ to allow for user entry) * Any additional comments (Open field) The above structure would allow for easy quantitation of preferred maps as a function of district/locale. Similar benefits could come from having such a structure for the other topics. | 80
Hearing verbatim feedback in meetings is not value-add for the commission or the public. It would be better if attendees could up-vote messages live so that everyone can immediately see the quantifiable level of support for a given point rather than sporadic reiteration. This would also allow more objective comparison of feedback across meetings. | 81
Explore the options, opportunity, and feasibility of establishing a Redistricting Commission Advisory Group (RCAG) and provide the results of the findings to the appropriate governing agency --- The San Diego Association of Governments, County Board of Supervisors --- for final determination. | 82
Explore the options and opportunities and feasibility of establishing a continuity of operations and succession plan, including a pool of Alternate Commissioners. Alternate Commissioners would be identified during the selection process, receive requisite training requirements, and attend all meetings to be immediately ready serve when required. | 83
Use performance based contracting. Ensure the process is deliberate, concise, and demanding and ensure discrete SOW line items are included with quantifiable deliverables. Onboard a dedicated journalist to avoid Commissioners creating independent material for publication. | 84
Onboard VRA, RPV and other specialized subject matter experts during the initial stages of the redistricting process and ensure they are readily available to support the process. | 85
Consider small working groups to discuss and process information and especially to level-set among comm'rs understanding of COI data, mapping process, and ideas for line drawing (responding to COI input and Census data). Working group meetings can be streamed live via zoom &/or recorded for transparency. | 86
To increase the pool of diverse applicants that may have financial barriers to participating (mostly younger adults with families, college students, non-retired adults), I would suggest offering a symbolic stipend (flat per diem rate) for each meeting attended. | 87
The IRC should choose the doctrines that define its operating structure and decision making paradigm. The new IRC should make the decision about staffing and personnel. A transition team should conduct analysis and provide options and recommendations to the new incoming IRC. The County should provide interim staff until a decision is made. | 88
If a demographic professional is not selected as an IRC Commissioner, a professional demographer should be hired to both educate the IRC Commissioners and to act as liaison and interface to the selected demographic contractor. | 89
Make use of the County personnel available as support staff. Have them prepare and post the agenda, minutes and attachments of the upcoming meetings. Also the budget worksheet and meeting setup, timeliness and protocol of the meetings, The clerk will be the timekeeper and announcer of the meetings. | 90
The County should ensure that any county staff working for the IRC have safeguards in place to protect IRC independence from the Board of Supervisors. The Clerk of the IRC should explain requirements and expectations for staff independence at the first full IRC meeting. The IRC, especially officers, should be clear on tasks & deadlines. | 91
The IRC selection process should remain the same, perhaps with additional energy spent on encouraging applications from hard-to-reach County residents. | 92
County staff could work with previous IRC commissioners & civic leaders to expand the pool of applicants & build an effective intern program. | 93
County staff did a great job supporting IRC. But it seems unfair to make them split their time between IRC and regular county position. Given the demands they faced to meet expectations and aggressive timelines of the IRC they should be 100% IRC. | 94
Retain as many members of our excellent staff as possible for future redistricting commissions. | 95
Hire demographer earlier. | 96
Require demographer provide mapping software to commissioners for testing prior to hire. Not a demo of the software, the actual software, so that commissioners can evaluate usability before deciding on which demographer to hire. | 97
The IRC should be the decision-maker on contracted services; that is not the case if the County process has a committee comprised of 3 voting members from county staff and 2 voting members from the IRC. The County should update this process to be the reverse for any case where the commission is truly supposed to be independent. | 98
Hire Voting Rights Act Special Counsel earlier. | 99
The consistent feedback from East County was that limited internet availability meant they did not know about the redistricting process early on. Demographers should be aware of internet availability across the County and address outreach accordingly. | 100
Hire Ability to Elect Consultant earlier. | 101
Require proposed statistical process as part of proposal during hiring process for Ability to Elect Consultant. | 102
Identify and assign functional staff SMEs in direct support of Commissioners in executing their duties and responsibilities as SPOCs and Committee members. | 103
Recommend 2030 IRC consider other processes for retaining contractors. Quickly assemble task force to research all options and resolve to hire ALL contractors, especially demographer and expert counsel as early in the timeline as possible. (See other comment about necessity of outside contractor for outreach/comm). Do not wait to hire contractors. | 104
When the map adoption deadline was extended to 12-15-21, general counsel services contract should have been extended to accommodate extension, an oversight on the part of, frankly, everyone. The 2030 IRC will need general counsel services 1-2 months beyond deadline and prospectively plan for that, provided by either outside counsel or the County. | 105
The Commission should no longer depend upon or use the existing County of San Diego Department of Purchasing and Procurement. An Executive Director hired by the IRC to be responsible for these decisions will create autonomy from the County of San Diego and will allow flexibility for the IRC to develop the Scope of Work, Contract, Selection Criteria, and Budget, while maintaining a fair application and interview process administered by the Executive Director. | 106
Amend bylaws to clearly delineate and separate the Independent Redistricting Commission’s (IRC) administrative functions from its mapmaking duties by creating the position of the Executive Director (ED) of the Commission. The ED is not San Diego County staff but an independent, nonpartisan contractor hired by the IRC to take on and manage all hiring and procurement decisions and establish policies and procedures for the functioning of the IRC with final approval of the Commission. Other Commissions have a similar structure (e.g., California Citizens Redistricting Commission, LA County Redistricting Commission, Michigan Citizens Redistricting Commission) | 107
At the first meetings of the IRC, the first order of business should be to review and approve the draft RFPs for the Executive Director, General Counsel, and Special Redistricting Counsel. An interim General Counsel could be appointed by the County to facilitate this process but with the understanding that this interim General Counsel will step down once the new legal counsel is hired. A letter of consent must be ratified by the IRC at its first meeting. This written consent is provided under California State Bar’s Professional Rules of Conduct 1.8.6. The consent should occur at or before the time the lawyer has entered into agreement for, charged, or accepted the compensation, or as soon thereafter as reasonably practicable. Since the County pays this counsel before the full IRC is seated, it is an important document that establishes the independence of that counsel and the responsibilities it has to the client, the IRC. Thereafter, the IRC is responsible for hiring its own Legal Counsel and determining however many lawyers are needed to carry out its duties, from development of the redistricting map, to its approval, to handling any potential litigation matters post-approval. | 108
A full Standard Operating Procedure manual should be developed to hand off to the new IRC. | 109
The IRC must develop a credible rationale for why COSD districts matter to the individual voter beyond keeping organizational units (cities, communities, etc.) whole within a given district and not to divide identified COIs among districts to the extent possible. But it is usually not clear why this matters to the individual voter in a tangible way (e.g., better schools, improved traffic, better policing, more public recreation, etc.). Our briefing and publicity material should give a compelling rationale for why COSD districts matter beyond that we are a big County with a big budget. We should request that submitted public comment specifically tell us why COSD districting and district boundaries really impact their personal lives and convenience. | 110
IRC open meetings and public hearings should be held in appropriate venue locations more directly reflecting voter population distributions. There should be more such meetings in all regions of San Diego City and COSD coastal areas. | 111
Develop more effective means of communicating to the general COSD voting public who we are, what we do, and why it matters to them. Our message seems to get through to various special interest groups who can then direct their membership to communicate with us re their special interest concerns. The general public has equal interests in redistricting outcomes, but they must first be made aware of how redistricting practically effects them and the importance of letting us know how they feel. This can be done with a more extensive (and expensive) public outreach campaign. | 112
Prior to the next redistricting cycle in 2030, develop a policy among each of the relevant IRCs serving to improve coordination and cooperation for mutual benefit. For example, initial information presentations to public groups could jointly present the State, County, and local redistricting stories to include descriptions of current districts, the desire/need for public input, and the how/why of redistricting processes. The public hearings conducted by each IRC could on occasion be held jointly and receive joint testimony re often overlapping voter concerns and desires. | 113
Review Bylaws as soon commission is sworn in and update as needed. | 114
The IRC should establish a process to regularly and explicitly review all public inputs, especially on maps, to further make clear that nothing is accepted as is. One possibility would be to instruct the IRC demographer to provide routine updates on which inputs from the public might deserve review or reconsideration. | 115
The IRC should consider contacting all CPGs, tribes, and similar groups before and during pre-mapping public hearings to encourage attendance and participation in IRC hearings and meetings. The IRC may wish to send regular updates, including links to draft maps, to as many such bodies as possible during the mapping (DMPH) phase. | 116
Have individuals identify themselves as a group and have one group spokesman provide testimony. The time allotted for such a group presentation could be longer than 3 minutes. Hearing the same testimony over-and-over again takes time away from others who may have different issues. | 117
This requirement helped the independent commissioners to keep track of and budget their time very closely instead of having to vote to increase the meeting every 15 minutes. Something to consider. | 118
Continue to include alternative meeting options to support redistricting. | 119
While initially awkward, over time Commissioners became more comfortable with the Zoom format. Zoom meetings may be more efficient and productive and I would urge the 2030 IRC to continue meeting virtually especially for working groups, committees, etc. I do not recommend completely eliminating in-person meetings, however. | 120
Recommend seating full IRC earlier--by Sept 1. It is optimistic (unrealistic) to expect 14 strangers, likely with no redistricting or public commission experience, to learn/do what is needed in 4 months (Jan-Apr) before starting complex task of drawing new maps. 2020 IRC had from Jan-Sept before mapping; 2030 should get similar time. | 121
Recommend IRC spend time in advance determining numbering system to be used. Maintain map numbers as they evolve (revised map 1 becomes map 1a rather than map 4, e.g.). Use letters for district numbers in all cases, rather than nicknames or #s, and use consistently from map to map (east county district is always Dist E, e.g). | 122
Recommend that 2030 IRC spend some time reviewing 2021 map, assessing its strengths and weaknesses, and considering revising it rather than starting with a blank slate. (Avoid bias towards blank slate approach.) | 123
Consider other options for how to handle interview requests, op-eds, other public engagement. On a 14-member commission, of 14 citizen volunteers, it is not necessary to funnel all of this activity through the one commissioner who already has numerous obligations. Comm'rs could apply for role; comm'rs could rotate in and out of role. | 124
Develop a clear policy for handling budget and contract amendments, even if such changes can be paid for with existing funds. Clarify whether approval is required in advance of changes and if so by whom and using what process-- chair/officers, staff (executive lead), or designated comm'r or committee. | 125
Review the statute that creates San Diego IRC and introduce legislation that would allow for the flexibility of any dates to be modified in the event of process delays. | 126
Would recommend conducting training earlier in the process. Perhaps through the development on publicly available online learning tools or providing early structured access to the Training Continuum. The current IRC should endeavor to provide a package of information to the next IRC which provides structured learning tools. | 127
Conduct several hourly information sessions providing an overview of the many existent County organizational and regional entities as well as COI and ethnic demographics, localities, and history. Such training could be given by SANDAG and COSD officials and relevant staff (e.g., the Registrar of Voters, SANDAG/County outreach staff) in addition to County-based educators and appropriate subject matter experts. | 128
Initial training should include Voter's Rights Act, Brown Act, Bylaws, 14th and 15th Amends to the US Constitution, racial polarity and prior files with notes and maps from the previous redistricting plan. Prior information should include all maps, contracts, agendas, meeting minutes, structure, timelines. | 129
Difficulties managing length of meetings. Allow 1 min per person, 3 minutes per group of 3, double if translation needed. Post rules in each agenda notes. Hold at least one public meeting is each district. Virtual and in person are preferred. | 130
Most of the public is not aware that there are redistricting commissions for the State, County, Local governments. All working on maps independently but simultaneously. Each commission draws a different map for a different purpose. Good idea to tell the public in your general education tour. | 131
The IRC could draw on the 2021 training continuum to guide updated training in light of new technological and legal developments, particularly with regard to mapping, communities of interest, and outreach. A more County-specific module on such features as unincorporated areas and hard-to-reach communities may be useful. | 132
The full IRC may want to consider hosting a social event or video conference with former redistricting Commissioners. The IRC may also want to consider joint training opportunities as a means to establish contact and exchange ideas with other local and regional commissions. | 133
Put together a training program on various geographic entities in SD County and implications if they are split. | 134
Briefing on fire districts and planning groups locations | 135
Train the communications and outreach consultant on using the mapping tool and build in public demo/training into the communications consultant scope. | 136
Include training, education, and materials to demonstrate pros and cons of different styles of map submissions to emphasize importance of small COI geographies. | 137
Have Commissioners attend or at least get detailed recaps of the Board of Supervisors meetings, especially early in the process. It will be useful for commissioners to have a deep understanding of the types of questions/issues that the Supervisors address so that the needs of each constituency can be better understood. | 138
Review IRDC training and education plan framework and process to maximize its effectiveness and efficiency. | 139
Conduct and incorporate E/EIS into the redistricting training and education, and map drawing process. | 140
Add training module: primer on IRC, commissioner duties, activities, bylaws, possible committee memberships, and other general onboarding (email, contacts). Specific topics to include what comm'rs can do (outreach, e.g.). Important for all comm'rs be on an equal playing field re access to info, staff, and other comm'rs. | 141
Add training module: Training on County jurisdictions and governance (various city and county comm planning groups, fire districts etc.) and a review of the county regions, populations, existing known COIs. This info is essential in mapping and has implications in line drawing decisions. | 142
More mapping training and consider doing some of this training early, often (repeatedly) and in small working groups. | 143
Assign comm'rs with expertise or interest to Budget & Finance Comm or Working Group to begin working with staff to develop a budget for approval by full IRC. | 144
Consider another format for lessons learned and begin compiling earlier. Research possibility of adhoc comm compiling submissions without violating Brown Act. Add categories for Mapping, Committees, Legal, Contractors. Combine some topics into one category (Policy/Doctrine/Bylaws). Clarify topics under each category. | 145