SAN DIEGO COUNTY SDF ANNUAL REPORT

FY 2004-05 


SPECIAL DISTRIBUTION FUND (SDF) ANNUAL REPORT

ON ALLOCATIONS BY THE INDIAN GAMING LOCAL COMMUNITY BENEFIT COMMITTEE (IGLCBC)

COUNTY OF SAN DIEGO

MARCH 29, 2005

TOTAL SDF ALLOCATION TO COUNTY:

$4,157,877.25

TOTAL SDF ALLOCATED BY IGLCBC:

$4,157,877.25
TOTAL SDF UNALLOCATED BY IGLCBC:

N/A

COUNTY ADMINISTRATIVE COSTS:


$26,000

TOTAL ALLOCATIONS TO PROJECTS:

$4,131,772.25
EXPENDITURES TO DATE:



$1,589,942.15

TOTAL UNSPENT ALLOCATIONS TO DATE:

$2,541,830.10

TOTAL NUMBER OF PROJECTS FUNDED:

7

CONTACT PERSON:

Name:
Chantal Saipe 

Title:

Tribal Liaison

Phone:
(619) 685-2542               

Fax:

(619) 531-5476 

E-mail Address:
chantal.saipe@sdcounty.ca.gov
	San Diego County Sheriff’s Department: for a medium lift fire/search & rescue helicopter to augment the Sheriff’s aviation detail

	$1,710,936
	NONE but funds have been encumbered for purchase.  Full payment will be made when helicopter is delivered.
	N/A
	$1,710,936
	Helicopter will be delivered and operational in June 2005.

	San Diego County District Attorney’s Office for the tribal liaison project


	$100,000
	$100,000
	Funding partially offset annual salaries and benefits for one full-time District Attorney Investigator, who serves as the Tribal Liaison; and two part-time Deputy District Attorneys, who work with Tribal Liaison to provide legal advice and prosecution support.
	NONE
	N/A

	Intermountain Fire Department - Construction of new fire station


	$111,772.25
	$75,870.60
	Construction related services
	$35,901.65
	Remaining funds will be allocated for expenditure by end of April 2005, and full disbursement by end of May 2005.  Funds will be used for paving of parking area, installation of heating and air conditioning, completion of interior, lighting and electrical.



	Heartland Communications Authority for a computerized emergency dispatch system


	$73,800
	$73,627.60
	Software and hardware were purchased to implement the Medical Priority Dispatch System and the Emergency Medical Dispatch Protocol.  Training on both systems has been held.
	$172.40
	Supplies for training 

	San Diego Rural Fire Protection District for a collaborative dispatch system.


	$100,000
	$26,795.09
	Funding has and will be used as a 50% match for dispatch services for 15 fire districts/volunteer fire depts.


	$73,204.91
	Remaining funds will be dispersed as invoices are received from the dispatch provider, Heartland Communications Facility Authority.  The grant should be exhausted by middle of July 2005.

	City of San Diego for Regional Fire and Rescue Helicopter Program


	$320,417
	$170,417
	Lease and operation of Copter One.
	$150,000
	Remaining funds have been set aside to reimburse the Sycuan Golden Eagle Flycrew for their services.



	Regional Type 1 Fire Apparatus Acquisitions for the following fire protection districts: East County; Alpine; San Miguel; San Diego Rural; and Lakeside Fire Protection Districts.
	$1,714,845.41
	Approximately $1,143,230.28
	East County used its funding of $285,807.57 towards purchase of Ferrara brand Type 1 Fire Apparatus.

San Diego Rural used funding of $285,807.57 towards purchase of two Urban-Interface Type II fire engines.

San Miguel Fire District used its funding of $571,615.14 towards purchase of three Type I Pierce brand fire engines.


	NONE

NONE

NONE

Lakeside and Alpine each has yet to spend their share of $285,807.57 so $571,615.14 remains.


	N/A

N/A

N/A

Lakeside will spend all its funding upon delivery of the Type III Brush Fire Engine it has ordered.

Alpine ordered a KME brand Type I fire Apparatus in September 2004.  Full payment will be made upon delivery of fire apparatus.


PAGE  
2

